Evaluation of “Reaching Across Borders” HIV Prevention Care and Treatment for Nepali Migrants at Source and Destination Communities In Nepal and India Supported by Family Health International

The Migrant Worker’s Trail HIV/AIDS And Roads to Recovery In Far-Western Nepal

Submitted to Social Welfare Council, Lainchaour, Kathmandu, Nepal by project evaluation team leader: Ms. Aparna Bhatta, 5 May, 2009

Acknowledgements

The Evaluation team wishes to acknowledge all those untold lakhs of humble hard working Nepalese labourers who through endemic poverty in their homeland have felt compelled to leave their families behind and journey to India to seek a slender livelihood. We particularly wish to recognise the tragic misfortune of those who have returned carrying the HIV virus and unknowingly passing it to their love ones.

This review is written with the hope that their suffering has not been in vain and that determined action will be taken to address the root causes of poverty and injustice and set this country on a path to sustainable development which is the birth right of every Nepalese citizen. We also wish to pay special tribute to all those courageous and compassionate individuals who have put their heart and soul into fighting the battle against the spread of HIV and who provide care and support for those who have fallen-victim to this modern epidemic.

Finally we wish to acknowledge the special role played by Family Health International in advancing this important cause particularly over the past three years through the RAB project. We wish to thank the Social Welfare Council for entrusting us with this review and for their assistance received. Last but not least we wish to recognise the participation of all those with whom we came into contact during our field visit but are too numerous to mention individually.

Table of Contents

| SECTION I - INTRODUCTION | 1 |
| --- | --- |
| 1.1 Project Background | 1 |
| 1.2 Project Objectives | 2 |
| 1.3 Intended Outcomes of the Project | 3 |
| 1.4 Intended Beneficiaries of the Project | 4 |
| 1.5 Donor Information | 4 |
| 1.6 Project Composition | 5 |
| 1.7 Financing Arrangements | 5 |
| 1.8 Objectives of the Evaluation | 6 |
| 1.9 Scope of the Evaluation | 6 |
| 1.10 Evaluation Research Questions | 7 |
| SECTION II – METHODOLOGY of EVALUATION | 8 |
| 2.1 Study Approach | 8 |
| 2.2 Study Designs | 8 |
| 2.3 Selection of Participants | 9 |
| 2.4 Study Instruments / Tools of Data Collection | 9 |
| 2.5 Data Presentation and Analysis Techniques | 9 |
| 2.6 Limitations of Study | 10 |
| SECTION III – DATA PRESENTATION and ANALYSIS | 11 |
| 3.1 Evaluation Field Visit Journal | 11 |
| 3.2 In-Depth Interview Questionnaire Results | 21 |
| 3.2.1 Part A Managerial – Interviews with Senior Members of Implementing Agencies | 21 |
| 3.2.2 Part B: Interviews with Clinicians and Laboratory Staff | 24 |
| 3.2.3 Part C&D: Interviews with Patients at Clinics and at Home | 25 |
| 3.2.4 Part F: Interviews with Project Owners | 26 |
| 3.3 Focus Group Meetings | 27 |
| 3.3.1 Discussion Group No.1 | 28 |
| 3.3.2 Discussion Group No.2 | 29 |
| 3.3.3 Discussion Group No.3 | 30 |
| 3.3.4 Success Story | 30 |
| 3.4 Personal Profiles – Mini Case Studies | 31 |
| 3.4.1 Case Study No.1 | 32 |
| 3.4.2 Case Study No.2 | 33 |
| 3.4.3 Case Study No.3 | 35 |
| 3.5 Financial Evaluation of the RAB Project | 37 |
| 3.5.1 Background | 37 |
| 3.5.2 Budget Estimate and Source of Funding | 37 |
| 3.5.3 Scope of Work for Financial Evaluation | 37 |
| 3.5.4 Financial Evaluation Methodology | 37 |
| 3.5.5 Financial Rules and Observations | 37 |
| 3.5.6 Comparison of Budget and Actual Expenditure | 38 |
| 3.5.7 Procurement of Goods and Services | 38 |
| 3.5.8 Compliance with General Agreement/ Project Agreements | 39 |
| 3.5.9 Compliance with Tax Laws | 40 |
| 3.5.10 Record of Fixed Assets | 40 |
| 3.5.11 Financial System/ Reporting & Internal Control System | 41 |
| 3.5.12 Comparison of Budget and Actual with Committed Project Costs | 42 |
| 3.5.13 Recommendations | 42 |
| SECTION IV– SUMMARY, CONCLUSIONS and RECOMMENDATIONS | 44 |
| 4.1 Summary – Analysis of Findings | 44 |
| 4.1.1 Migration, Demography, Risk Behaviour, and HIV Prevalence | 44 |
| 4.1.2 HIV Awareness and Behaviour Change | 45 |
| 4.1.3 Radio Listener’s Groups | 47 |
| 4.1.4 Reaching Across Borders | 47 |
| 4.1.5 Clinical Workload, Hospital Health Priorities and Sustainability | 48 |
| 4.1.6 O.I. Therapy | 48 |
| 4.1.7 Patients’ Perspectives | 49 |
| 4.1.8 Poverty Root Cause and Need for Comprehensive Development | 49 |
| 4.1.9 Analysis of Community Resource Mobilisation and Sustainability | 50 |
| 4.1.10 Project Structure Analysis | 51 |
| 4.1.11 SMART Objectives | 55 |
| 4.1.12 Control and NGO Participation | 55 |
| 4.1.13 Strategic Focus | 55 |
| 4.1.14 Achievements | 56 |
| 4.1.15 Effectiveness over Time | 56 |
| 4.2 Conclusions | 57 |
| 4.2.1 HIV Epidemic | 57 |
| 4.2.2 Awareness and Behaviour Change | 57 |
| 4.2.3 Cross Border Reach | 57 |
| 4.2.4 Poverty Alleviation and Comprehensive Development | 58 |
| 4.2.5 Radio Listener’s Groups | 58 |
| 4.2.6 Leveraging Community Resources for Sustainability | 58 |
| 4.2.7 O.I. Therapy and Nutrition | 59 |
| 4.2.8 Patient Centred Responses | 59 |
| 4.2.9 Project Definition | 59 |
| 4.2.10 Partner Agency Participation | 60 |
| 4.2.11 Project Structure and Definition | 60 |
| 4.3 Recommendations | 62 |
| 4.3.1 HIV Epidemic | 62 |
| 4.3.2 Awareness and Behaviour Change | 62 |
| 4.3.3 Cross Border Reach | 62 |
| 4.3.4 Poverty Alleviation and Comprehensive Development | 62 |
| 4.3.5 Radio Listener’s Groups | 62 |
| 4.3.6 Leveraging Community Resources for Sustainability | 62 |
| 4.3.7 O.I. Therapy and Nutrition | 63 |
| 4.3.8 Patient Centred Responses | 63 |
| 4.3.9 Project Definition | 63 |
| 4.3.10 Partner Agency Participation | 63 |
| 4.3.11 Project Structure and Definition | 63 |
| SECTION V – REFERENCES | 64 |
| SECTION VI – ANNEXTURES | 65 |
| 6.1 Field Questionnaire | 65 |
| 6.1.1 Part A: Managerial | 66 |
| 6.1.2 Part B: Technical | 71 |
| 6.1.3 Part C: Patient at Clinic | 73 |
| 6.1.4 Part D: Patient at Home | 76 |
| 6.1.5 Part E: Financial | 79 |
| 6.1.6 Part F: Project Owner | 82 |
| 6.2 Photographs from Field Visit with Captions | 84 |
| SECTION VII – APPENDICES | 87 |
| 7.1 Project Logical Framework | 87 |

List of Tables

| The Budget Estimate for Entire Project Tenure | 37 |
| --- | --- |
| Comparative Details of Budget (revised) and Actual Project Cost | 42 |
| Project Structure Analysis Table | 53 |
| Project Budget Breakdown by Programme | 57 |
| Hypothetical Value Created Through Project Activities vs Total Project Budget | 58 |

List of Annexure

| 6.1 Field Questionnaire | 64 |
| --- | --- |
| 6.1.1 Part A: Managerial | 66 |
| 6.1.2 Part B: Technical | 71 |
| 6.1.3 Part C: Patient at Clinic | 73 |
| 6.1.4 Part D: Patient at Home | 76 |
| 6.1.5 Part E: Financial | 79 |
| 6.1.6 Part F: Project Owner | 82 |
| 6.2 Photographs from Field Visit with Captions | 84 |

List of Appendices

| 7.1 Project Logical Framework | 90 |
| --- | --- |
| 7.2 FHI Responses to Draft Report | 92 |

List of Abbreviations

| AIDS | Acquired Immune Deficiency Syndrome |
| --- | --- |
| APRO | Asia Pacific Religion office{FHI} |
| ART | Antiretroviral Therapy |
| ARV | Antiretroviral{drug} |
| BCI | Behaviour Change Intervention |
| CBO | Community Based Organization |
| CDF | Community Development Forum |
| CDO | Chief District Officer |
| CHBC | Community Home Based Care |
| DACC | District Aids Coordination Committee |
| DDC | District Development Committees |
| DFID | Department For International Development, UK |
| EPC | Essential Package for Care |
| FHI | Family Health International |
| GON | Government Of Nepal |
| GTZ | German Technical Cooperation |
| HBC | Home Based Care |
| HIV | Human Immunodeficiency Virus |
| IBBS | Integrated Behavioural and Biological Survey |
| ICC | Information Council Centre |
| INGO | International Non-Governmental Organization |
| MOH | Ministry Of Health |
| N’ SARC | Nepal STD and AIDS Research Centre |
| NCASC | National Centre for AIDS and STD control |
| NGO | Non-Governmental Organization |
| NKP | Nava Kiran Plus |
| NRCS | National Red Cross Society |
| OI | Opportunistic Infection |
| PHC | Primary health Care centre |
| PLHA | People living with HIV/AIDS |
| PMIS | Patient Management Information System |
| PMTCT | Prevention of Mother to Child Transmission |
| PSA | Public Service Agreement |
| RAB | Reaching Across Borders Project |
| RPA | Radio Public Awareness Club |
| SAC | Social Awareness Centre |
| SCF | Save the Children Federation |
| STEP | Stepping Together for Educational Problem |
| STI | Sexually Transmitted Infection |
| SWC | Social Welfare Council |
| TB | Tuberculosis |
| UNDP | United Nations Development Programme |
| UNICEF | United Nation’s Children Fund |
| USAID | Untied States Agency for International Development |
| VAT | Value Added Tax |
| VCT | Voluntary Counselling and Testing |
| VDC | Village Development Committee |
| WHO | World Health Organization |

Executive Summary

“Reaching across Borders – HIV Prevention Care and Treatment for Nepali Migrants at Source and Destination Communities in Nepal and India” is essentially a repackaging of earlier and some new initiatives in the same project areas and programmatic field, with the aim of providing an ongoing comprehensive response to the current HIV/AIDS crisis particularly in Far-Western regions of Nepal and several popular migration destinations in India.

The RAB project has been under the responsibility of Family Health International for the period from second quarter 2006 to first quarter 2009 with field activities implemented through a total of eight agencies including three Government Hospitals and five local non-Government organisations. This evaluation has been conducted on behalf of The Social Welfare Council of Nepal.

Focus on Care and Treatment
The evaluation found a clear focus on care and treatment for persons living with HIV/AIDS (PLHA’s). The project has made a considerable contribution to the strengthening of the Government hospital system’s responses to the HIV crisis through substantial input in areas including upgrading outpatient departments, facilitating installation of laboratory and test equipment, training clinical staff, building essential information infrastructure such as drug inventory and patient record systems, and involving NGO’s in service delivery to PLHA’s in overburdened hospital wards and clinics.

Community Based Responses to HIV Crisis
The evaluation also found that RAB has made great strides in strengthening community responses to the HIV crisis particularly through training and organising the voluntary sector. Highlight included the establishment of community based care teams including both NGO professionals and building of PLHA support groups principally for drug therapy continuance together with organisational capacity building among the supporting NGO’s. There was also an impressive range of NGO operated community outreach activities aimed at creating HIV awareness, encouraging voluntary testing and advising on safer sex.

Public vs Community Responses
The review found that RAB has injected significant support and real resources into supporting the Government hospital system’s responses to the HIV/AIDS crisis. Despite this support the publicly operated health system remains overburdened, underfunded and unable to give HIV a higher priority. By comparison project support to NGO’s has yielded excellent results through compassionate dedicated care yet this sector lacks paramedical and nursing skills. The development of community home-based care is considered to be an outstanding example of community care. The evaluation suggests that sustainable service delivery to PLHA’s needs to be refocused on the voluntary and community agencies thereby relieving pressure on the hospital health system allowing it to concentrate more on acute care. The evaluation further recommends that opportunities be grasped to institutionalise these gains by developing existing NGO’s into Social Enterprises addressing a holistic approach including ongoing care and treatment, rehabilitation, poverty alleviation, personal development and community based economic development.

Reaching across Borders
The evaluation found that despite strong initial intentions, the project had addressed itself to the core theme of reaching across borders only to a very limited extent, that a referral system to enable drug continuance for PLHA migrants was at best only partially successful, that PLHA support coverage in India was limited. There was particular concern about the status of cross border cooperation in prevention and support activities with sites in India, particularly project outputs 3 & 4 which appeared to have dropped off or been abandoned with the allocated funding unaccounted for. The evaluation wishes to recommend that irrespective of the status of these activities, future programmes in this area focus of developing strong links to existing PLHA support networks through many regions of India rather than attempting to build their own services in a few locations.

HIV Prevention
Concerning the prevention programme, the evaluation found that despite its high profile only one third of project resources were allocated to this area and that overall it was a secondary priority after treatment and care. Nevertheless this review recognises the project’s claimed outreach achievements in contacting around 100,000 persons for imparting prevention messages. While this evaluation applauds the intent of outreach particularly as a means of attracting subjects for voluntary counselling and testing (VCT). No statistical or research tools were available to measure or assess the effectiveness of the prevention message and there was concern that the programme may not be reaching the most ‘at-risk’. The evaluation considers outreach ‘at best’ a medium to longer term programme for creating awareness and that its message needs to be focussed on youth not yet of fixed habit and attitude.

In seeking hard facts, the review considers the achievement of a total of 10,000 VCT and STI tests to be the main tangible outcome of the outreach programme in contacting 100,000 persons and in this respect the project can be considered to have demonstrated an effective contact ratio of 1:10.  This review recommends this ratio be deemed a key management indicator and that future work in this area to focus on narrowing the ratio through greatly expanded testing as the surest way to improve programme effectiveness. It further wishes to recommend that in the face of a public health crisis, testing be presented as a ‘Social responsibilities’. The review also recommends that any expanded programme of testing incorporate serious efforts to build a statistical demographic information database to help continually guide and direct its activities and support the larger fight to halt the current concern over rising people with HIV/AIDS.

Epidemic Fighting
The review was concerned that despite the projects stated intention of supporting Nepal’s millennium target no.6 of halting the spread of HIV by 2015, it did not seem to be at the forefront of this efforts with no clear strategy. To this end the project proposal did not contain any estimate of the size of the target group. The review was also concerned about widely conflicting evidence as to the HIV prevalence rate among the target group and whether this project could or should be contributing to research models to help the rising rate of HIV. Overall the review wishes to recommend that further activity focus on more efforts including combined work with other INGO and Government agencies to help PLHA’s  and susceptible group.

HIV Poverty and INGO Support for Development
The review was presented with strong ‘grass-roots’ arguments in support of the view that pervasive poverty, injustice, marginalisation, discrimination, and underdevelopment are at the root of the massive labour migration and numerous social problems including HIV/AIDS. The review wishes to pass on field level recommendations urging SWC and NCASC to encourage INGO’s to join broad regional anti-poverty and pro-development initiatives rather than to scatter their resources or spread themselves too thinly in trying to do everything. This review wishes to add its voice to this chorus and suggest that longer term HIV prevention is likely to be more effective and more meaningful when presented in the context of community based development instead of stand alone or single agenda interventions.

O.I. Therapy
The evaluation has found that practically all PLHA’s exist in a state of poverty with inadequate diets and enjoy few life options. While the RAB project can be commended for having achieved a universal free ART drug regime the same cannot be said about the provision of medicines for Opportunistic Infections (O.I.) where many necessary drugs are either unavailable or not available free of charge. In addition there is a near universal need for nutritional supplementation among the PLHA community. This review is concerned that drug budgets need to be reworked to include realistic estimates for I.O. medicines and dietary supplementation.

Partner Agency Participation
The evaluation found that partner agencies were not sufficiently involved in the project definition and control, being treated more as sub-contractors rather than genuine partners whose ideas and contributions were highly valued. It is recommended that any revision of the project needs to include high levels of partner participation in the full project cycle including planning, definition, monitoring and evaluation.

Project Structure
It is considered that several of the observed weaknesses in the project appear to stem from structural problems which in turn may have been inherited from earlier arrangements. The project has been organised around two main thrusts:

- Treatment and Care

- HIV Prevention

Yet it is further observed that these two areas have received unequal resources, support and strategic focus, and that the common management system has tended to inhibit innovation and the development of the prevention programme. While the centralised management style may be highly appropriate for the well defined medical responses to HIV care and treatment, it is considered to be less appropriate in the prevention area which needs focussed leadership that is prepared to take risks and rewards innovation especially in the creation of media materials and methods to reach the seriously at-risk in the target group. Furthermore, the present prevention programme appears to be pedestrian in its approach and far more suitable for a medium to long term programme than for an immediate response to a crisis.

It is recommended the project be redefined around these objectives:

- Care and Treatment for PLHA with emphasis on rehabilitation and economic development

- Medium to Long Term HIV awareness and education built into broad community development and poverty eradication programmes

It is further recommended that each of these complementary objectives be given form through separate but inter-connected programmes with clear strategic vision and dedicated leadership.

Closing
The evaluation team wishes to thank SWC for this assignment and the opportunity to gain a deeper insight into the field of HIV prevention and Care. We recognise that this is an immensely difficult and challenging field in which to work and while some aspects of the evaluation may appear critical, the team nevertheless wishes to commend FHI and its partners for taking on this project and for the very real achievements and contributions they have made towards alleviating human suffering

Caveat
The evaluation team wishes to apologise in advance for any errors and omissions that may be found in this report.

SECTION I
INTRODUCTION

  - Project Background

Family Health International (FHI) Nepal has been managing a programme as per the general and project agreement signed with the Social Welfare Council (SWC). This ‘Terms of Reference’ (TOR) is designed for evaluating the project/program as per the Project Agreement signed between/among the Social Welfare Council (SWC) and FHI on 1 February 2006

- Name of the Project and its location: 
“Reaching Across Borders” Project 
HIV prevention, care and treatment for Nepali migrants at source and destination communities in Nepal and India

- Period of Project Effectiveness: 
February 2006 through February 2009

- Name of the Partner NGO/s and Location/s:

| Social Awareness Centre | Birendranagar, Surkhet |
| --- | --- |
| Community Development Forum | Ward #1 Dipayal, Doti |
| Nepal Red Cross Society, Kailali | Main Road Dhangadi, Kailali |
| Nepal STD and AIDS Research Centre | Nepalgunj, Banke |
| Nava Kiran Plus (NKP) | Hasanpur, Dhangadi, Kailali |

As early as 2003 it was estimated, by FHI and others that between 30%-50% of the current HIV burden in Nepal can be attributed to risks associated with migration. It was further estimated that between 600,000 and 1,200,000 million men migrate annually to India for work. Labour migration is directly related to endemic poverty (national average 31%) with source communities located throughout Nepal. The project focused on a cluster of source communities in the far western region of Nepal and destination locations in India with high HIV prevalence rates, principally Mumbai, Thane, and Delhi.

The original proposal outlined a three year cross-border initiative to reduce HIV transmission and increase access to treatment and care for Nepali migrant workers in selected source communities in the far western region and destination locations in India.  Expected outcomes included greater condom use and uptake of HIV treatment and care including voluntary counselling and testing (VCT), prophylaxis and treatment for opportunistic infections (OI), TB diagnosis and treatment, and anti-retroviral therapy (ART) for HIV positive migrant workers and their families.

Nepal is classified as a ‘Least Developed Low Income’ country that ranks lowly at 140 in the UN ‘human development index’ published in 2004. Poverty, deprivation, and discrimination are underlying causes of poor development in Nepal. It is also considered to be a fragile state that has suffered from protracted civil conflict over at least a decade and is now host to a concentrated HIV epidemic. The project promoters acknowledge that this is a demanding context in which to develop an effective national response to HIV. They also recognise that Nepal’s ability to maintain a national response and improve access to treatment and care for persons living with HIV/AIDS (PLHA) will largely depend on external funding assistance.  The project is also intended to contribute to Nepal’s efforts to achieve its Millennium Development Target No.6 ‘halting the spread of HIV by 2015’.

The project focused on conflict affected areas in the far western region that are also a major source of worker migration to India and builds on the earlier, USAID funded, ‘Nepal-India Safer Migration Initiative’. It also aimed to draw on lessons learned in Cambodia and Thailand in scaling up access to care and treatment while developing an innovative model for ART delivery and commodity security. The project also intended to enable cross border efforts in HIV prevention and continuity of access to care and treatment for HIV positive migrant workers and their families.

  - Project Objectives

Goal, Purpose, Outputs and Objective Themes

The RAB project ‘Logical Framework’ (refer Appendix 1) describes a hierarchy comprising a Goal, a Purpose, and a series of Outputs and associated Activities. These headings contain a mixture of goal, objectives, and programmatic themes.

Goal

The project Goal is stated as:

“Reduced HIV transmission and increased access to treatment and care amongst Nepali migrants in source communities in Far West Nepal and destination communities in India”

Purpose

The project logical framework provides a statement of purpose, expressed as:

“Increase condom use by male Nepali migrants and increase uptake of VCT, STI and HIV care and treatment amongst Nepali male and female migrants and their families in source and destination areas in Nepal and India”

Outputs

The logical framework proceeds to describe a set of five ‘Outputs’ which are limited to providing descriptions of the various programmes.

- Expansion of the Safer Migration Initiative HIV prevention activities to Doti district in Far West Nepal

- Establishment of a care and treatment service for HIV positive Nepali migrants and their families in Mahendranagar and Dhangadi in Far West Nepal

- Continuation and strengthening of existing HIV prevention activities for Nepal male migrants and their families in Mumbai and Thane

- Programmatic expansion of services in Mumbai and Thane to include limited scale care and treatment services for Nepali migrants and their families

- Extension of prevention activities to Surkhet and establishment of a care and treatment service for HIV positive migrants and their families in Kailali

Objectives

Analysis of the various statements of Goal, Purpose, Outputs, and Activities contained in the ‘Logical Framework’ (refer Appendix 1) enabled the review to isolate the implied objective themes from programmatic descriptive material. This analysis produced two major objective headings and three objective themes, otherwise described as programmes, under each heading making a total of six objectives themes. The product of this work is described in detail in an analysis of Goal and Objectives contained in Section IV paragraph 4.1.10 Project Structure Analysis

1.3 Intended Outcomes of the Project

As discussed in the previous section, the project documentation expresses objectives in very general statements and descriptions of programmes. Owing to the relative scarcity of specific, measureable and time-bound objectives it has been difficult to precisely identify the outcomes intended by the authors. However specific numerical targets are associated with several of the project activities allowing project performance to be partially gauged in these areas. Overall the review is necessarily limited to considering the stated outputs and describing the actual situation within each of these programmatic areas as it was found on the ground.

Outputs:

- Expansion of the Safer Migration Initiative HIV prevention activities to Doti district in Far West Nepal

- Establishment of a care and treatment service for HIV positive Nepali migrants and their families in Mahendranagar and Dhangadi in Far West Nepal

- Continuation and strengthening of existing HIV prevention activities for Nepal male migrants and their families in Mumbai and Thane

- Programmatic expansion of services in Mumbai and Thane to include limited scale care and treatment services for Nepali migrants and their families

- Extension of prevention activities to Surkhet and establishment of a care and treatment service for HIV positive migrants and their families in Kailali

Nevertheless, it appears that on the prevention side, the expected outcomes included greater HIV/AIDS awareness and reduction of risk behaviour involving greater condom use, and on the treatment side, greater uptake of HIV treatment and care including voluntary counselling and testing (VCT), prophylaxis and treatment for opportunistic infections (OI), TB diagnosis and treatment, and anti-retroviral therapy (ART) for HIV positive migrant workers and their families.

Not all of these outcomes can be directly measured and in any case only a limited number of numerical targets appear to have been employed. These are:

Numerical Targets over Project Life

  - Extension of community based peer education to 25 VDC’s in Doti

  - Establish 40 radio listener’s groups

  - 80,000  individuals contacted for prevention education

  - 380 PLHA’s being treated through ARV therapy later amended to 590

  - 2,020 receiving treatment for STI’s and OI’s

  - 5,000 using clinical services

This area is discussed in detail in an analysis of Goal and Objectives contained in Section IV paragraph 4.1.10 Project Structure Analysis

1.4 Intended Beneficiaries of the Project

Throughout project documentation the intended beneficiaries are identified simply as:

‘Nepali male migrants and their families’

This is a class definition and the review has not been provided with any explicit qualifying factors that might help to determine the size of the potential target group and hence the number of beneficiaries or the expected numbers that might seek services from the various programmes.

The review however has assumed that the intended beneficiaries are limited to migrant workers (and their immediate families) who travel between far western districts of Nepal and locations in India, and who might be considered to be at risk of contracting HIV and thereby transmitting the disease causing virus to their home communities in Nepal.

1.5 Donor Information

# The RAB project was wholly funded by the UK Government through the Department for International Development DFID.

# The following summary information was extracted from DFID’s official website:

# About DFID

## Who are we and what are we doing to tackle world poverty?

The Department for International Development (DFID) is the part of the UK Government that manages Britain’s aid to poor countries and works to get rid of extreme poverty.

We are headed by a Cabinet minister, one of the senior ministers in the Government. This reflects how important the Government sees reducing poverty around the world. We have two headquarters (in London and East Kilbride, near Glasgow) and 64 offices overseas. We also have over 2500 staff, almost half of whom work abroad.

## What is development?

- When we talk about international development we are referring to efforts, by developed and developing countries, to bring people out of poverty and so reduce how much their country relies on overseas aid. Many different things can contribute to development which reduces poverty, such as settling conflicts, increasing trade, tackling climate change, securing more and better aid, and improving health and education.

## Why is the UK Government involved in development?

More than a billion people, one in five of the world’s population, live in extreme poverty. This means they live on less than 65p a day. Ten million children die before their fifth birthday, most of them from preventable diseases. More than 113 million children do not go to school.

In a world of growing wealth, such levels of human suffering and wasted potential are not only morally wrong, they are also against our own interests. We are becoming much closer to people in faraway countries. We trade more and more with people around the world.

Many of the problems which affect us, such as war and conflict, international crime, refugees, the trade in illegal drugs and the spread of diseases like HIV and AIDS, are caused or made worse by poverty in developing countries. Getting rid of poverty will make for a better world for everybody.

Making governance work for the poor – DFID’s third White Paper

1.6  Project Composition

The RAB project is implemented in Nepal through one INGO as the lead implementer, five local NGO’s and three government hospitals. These organisations and their respective roles and responsibilities are

- Social Awareness Centre – Surkhet – community based development

- Community Development Forum – Doti – Community based development and advocacy

- Nepal Red Cross Society – Kailali – Humanitarian and relief support providing Ambulance and Blood services, HIV/Aids awareness

- NSARC – Nepalgunj – HIV & STI prevention and testing services in mid-far west regions

- NKP – Kailali – PLHA support services

- FHI – Kathmandu and Dhanagadi – world wide research education and support in HIV/AIDS prevention and treatment

- Seti Zonal Hospital – Kailali – Base hospital for Seti Zone in Kailali district – provide acute in-patient care

- Mahakali Zonal Hospital –– Base hospital for Mahakali zone, Kanchanpur district – provide inpstient services for PLHA’s

- Doti District Hospital – Doti – Base hospital Doti district

Details of the community based NGO’s and implementer FHI are shown in the Appendix

1.7 Financing Arrangements

Budget Estimate and Source of Financing:

As per the initial project agreement the budget estimate for the entire project tenure was as follows:

| Particulars | Yr. 1 | Yr. 2 | Yr. 3 | Total | Percentage |
| --- | --- | --- | --- | --- | --- |
| Administrative/ overhead cost | 62,225 | 75,604 | 101,339 | 239,168 | 14.85 |
| Program cost | 197,121 | 570,367 | 604,419 | 1,371,907 | 85.15 |
| Total Amount (USD) | 259,346 | 645,971 | 705,758 | 1,611,075 | 100.00 |

The entire funding is to be provided by Department for international Development (DFID), Head Quarter (1 Palace Street London SW1E 5HE) as financial grant.

The financial evaluation is presented in SECTION III Data Presentation and Analysis

1.8 Objectives of the Evaluation

This project commenced in February 2006 and lasted until February 2009. The Social Welfare Council engaged an independent consultant for this review. The consultant reviewed documents, visited FHI offices in Kathmandu and Dhangadi, and met with partner NGO’s and community members in Dhangadi, Kailali and Doti districts.

The objectives of the project evaluation were to:

- explore the level of progress/changes made by the project and analyse the extent to which the achievements have supported the project goals and their objectives

- evaluate the project effectiveness – longitudinal effect and continuity of the project activities/services as well as the scope and extent of the institutionalisation of the project

- explore the cost effectiveness of the project activities

- identify the target and level of achievements as specified in the project agreement

- explore the coordination between the concerned line agencies in the project districts

- determine the income and expenditure in compliance with the project agreement and proportion of programmatic and administrative cost incurred by the project

- examine the financial disciplines in accordance with prevailing rules and regulations and disposition of fixed assets procured through duty free privileges and locally

- assess the good lessons to be replicated in other projects and aspects to be improved in future

1.9  Scope of the Evaluation

Based on the above said evaluation objectives the team was requested to concentrated on the assessment of the following issues:

  - Community/social/public auditing practices in the program/project areas.

  - I/NGO/project’s coordination mechanism with local bodies and other line agencies.

  - Level of public/community participation

  - The extent of social inclusion in the project implementation.

  - Impact of the project in the community.

  - I/NGO’s partnership modality/strategy with counterpart/partner and its contribution.

  - Extent of the level of up-to-date completion of the project activities.

  - Inventory/assets management system of the project/programs (records, uses and condition of durable goods purchased under duty exemption) maintained by the I/NGO/s.

  - Income and expenditure pattern of project/program and level of accounting transparency

  - Resource flow modality from I/NGO to partners and community

  - Internal financial control system of the project.

  - Sustainability component of the project/program.

  - Project’s target and achievements as per the log frame stipulated under project agreement.

  - Successful cases/stories of the project, which can be replicated in other areas/programs, and failure cases and the lesson to be learnt.

  - Contribution, role and responsibilities of foreign representative/ expatriate/ volunteers within the project/organization (if applicable).

  - Compliance with clause No. 1 of general agreement signed between SWC and INGO.

  - Socio-ethical issues governing the project implementation.

  - Review of findings and suggestions shown by previous monitoring and evaluation reports. (If applicable)

  - Evaluation Research Questions

The questions for this project evaluation were formulated to help assess the effectiveness of programme activities both during the currency of the project and its likely longer term impacts.

All the research questions are contained in the questionnaire forms

Refer to Annexure 6.1 Field Questionnaires

SECTION II
METHODOLOGY of EVALUATION

  - Study Approach

In consideration of limited time and resources the evaluation team decided that the evaluation would concentrated principally on a review of existing project documentation and in-depth interviews with project participants, including a SWOT analysis, observation at programmes sites, and a group meetings with participants and beneficiaries.

The document research involved examining:

- The original project proposal

- The original agreement between Social Welfare Council and Family Health International – Nepal

- Quarterly progress reports

- Mid-term review

Interviews with project participants were guided by a comprehensive set of questionnaires.

A discussion and SWOT analysis was incorporated to help gain an understanding of capacity building and reveal underlying issues among the various implementation groups

Another discussion group was arranged for beneficiaries

Finally observation was a key approach to quickly discovering the reality on the ground and testing other sources of information

  - Study Designs

As indicated above the method of the study was exploratory, impressionistic, and at times opportunistic. Recognising that information collection would necessarily involve a highly concentrated evaluation seven day field visit in the far west region covering Dhangadi, Kailali and Kanchanpur districts, the study design was worked out as far as possible with team members in advance of the visit. It was intended to employ four main means of information gathering including guided interviews, focus group discussion, informal discussion and direct observations.

Guided interviews
A total of six detailed questionnaires were prepared covering various classes of project participants and beneficiaries. These were:

- Part A Managerial – Interview Questions for senior members of implementing agencies involved with either Social and/or Clinical services

Ten interviews were administered to members of this group

- Part B Technical – Interview Questions for Clinicians and Laboratory Staff

Eight interviews were administered in this group

- Part C Patient at Clinic – Interview Questions for Patients

Eight interviews were administered with this group

- Part D Patient at Home – Interview Questions for Patients

Seven interviews were administered with this group

- Part E Financial – Interview Questions for senior managers responsible for Accounting and/or Financial Controls in implementing agencies

Seven interviews were administered with this group

- Part F Project Owner – Interview Questions for senior managers responsible for designing and promoting this Project

Questionnaire delivered to 4 senior managers but at time of writing the results were not yet received

Focus group
A focus group discussion was planned to be conducted in a multi disciplinary fashion involving managers and members of several key implementing NGO’s during which it was planned to conduct a SWOT analysis as a means to elicit participation and interaction. As it happened some 50 persons were available and the results of the SWOT were recorded on flip charts.

A second impromptu discussion group was arranged when an opportunity arose to meet with some 40 PLHA’s. This was a useful meeting held together with the evaluation team and members of the PLHA’s individual NGO support groups.

Observation
Informal discussion and incidental information gathering was to be organised through a series of observation visits to implementing agencies with detailed field notes taken by team members. As the itinerary worked out these sites included:

- FHI Central office

- FHI project office at Dhangadi

- Gopghat ICC outreach centre

- Panchanali Radio listener’s group

- CDF Doti

- Doti district hospital ART team

- Doti DHO, medical staff & DCC member

- NNSWA ART & VCT team

- Mahakali Zonal hospital ART team

- Malakheti VCT team

- Red Cross PLHA support group

- Seti Zonal Hospital ART centre

- Seti zonal medical superintendent, medical staff and committee chair

- N’SARC Kailali

- NKP Kailali

Key impressions and detailed observations were noted by the evaluation team members and constructed into a field journal which is presented in SECTION III

  - Selection of Participants

The evaluation field visit timetable did not allow for any elaborate appointment arrangements according to the wishes of the evaluation team. Instead FHI project office had made most of the field visit arrangements right down to logistics and schedules. Nevertheless the evaluation team exercised their discretion over whom they chose to interview, and the generally attempted to determine their own pace and style in the conduct of meetings and observations at the various institutions visited.

  - Study Instruments / Tools of Data Collection

As mentioned above the principal data collection mechanisms were

- Field Journal

- Questionnaire forms

Additional information was recorded in the:

- Focus group meeting and SWOT analysis

  - Data Presentation and Analysis Techniques

The in-depth interview questionnaires were hand summarised

  - Limitations of the Study

This study was constrained by extremely limited time and opportunity for field interaction considering the extensive scope and duration of the project. The Project Director was out of country at the time of the evaluation, and therefore the evaluation team had difficulty in obtaining much of the necessary input on time including quarterly project reports, mid term review, financial records, and even the required report format arrived well after the study began.

The fact that the evaluation was being conducted well after official termination of the FHI management of the project simply added to frustrations for the team since many of the key people were not present in the field or only marginally interested. During the field visit the team was rushed due to the tight field schedule and therefore may have missed critical information.   Many of the field staff was in a state of high anxiety owing to uncertainty about the future of activities as FHI was still waiting for approval for follow on funding for key activities, thus creating a generally tense environment.

The team required assistance from others due to the large amount of work that needed to be done. Documents had to be composed and formatted particularly data capture forms as in the questionnaires.

Sustainability

During evaluation team’s field visit, the evaluation team observed  how the implementing partners are benefiting at the field level  from  the intensive  training and orientation  to enhance  their institutional capacity mechanisms by ensuring  community participation which have been established  in the project areas. RAB project has made great strides in strengthening voluntary sector, NGOS, PLHA support groups and the government hospitals through training, supplying necessary equipment and resources.

Target vs. Achievements

| Numerical Targets | Achievements |
| --- | --- |
| 1. Extension of community based peer education to 25VDC’s in Doti | These targets were met. |
| 2. Establish 40 radio listener’s groups | These targets were met. |
| 3. 80,000 individuals contacted for prevention education. |  |
| 4. 380 PLHA’s being treated through ARV therapy later amended to 590 |  |
| 5. 2,020 receiving treatment STI’s and OI’s |  |
| 6. 5,000 using clinical services |  |

The first two of these targets were explicitly connected to project activities and by implication to an objective.  The other four are hard to identify as a clear cut achievements.

SECTION III
DATA PRESENTATION and ANALYSIS

3.1 Evaluation Field Visit Journal

From 20 March the Evaluation team undertook a schedule of evaluation review visits to projects sites. This commenced in Kathmandu on 20th with a visit to FHI central office.

The following day the team travelled to Dhangadi from where its members embarked on a seven day tour covering most of the key project sites in Far Western Nepal. The itinerary, field journal observations are shown in detail the following pages.

Evaluation Field Visit Journal

20-27 March 2009

| Date | Place | Activity/Meeting/Discussions | Observations, Impressions and Comments |
| --- | --- | --- | --- |
| 20/3 | Kathmandu | - Meeting with FHI central office staff | During this meeting FHI team members explained that the activities in India were reported on separately by FHI India Office. The FHI India office had a separate budget for the project and accounted for expenditures directly to FHI Asia Pacific Regional Office in Bangkok. The Project Director in charge of the overall budget was not in Nepal at the time of the interviews and the FHI staff were not in a position to discuss the overall $US1.6m RAB project budget cited in the proposal documents. FHI indicated that their organisation provided support and logistics for the installation of CD4 machines but negotiated with WHO/SEARO in Delhi to provide the actual CD4 machine. FHI staff advised that program activities are run by 5 NGOs and that this is a highly successful and most effective programme. It was stated that the programme is very sensitive and very hard to phase out within a short period of time. They also explained that FHI is proud that RAB is unique and has successfully been able to refer PLHA cases between India and Nepal. It was also mentioned that there was an on organisation in Delhi called Saathi that supported Nepali PLHA referral cases. Saathi’s is now registered as a local Indian NGO and is still operating with limited input from FHI. |
| 21/3 | Dhangadi | - Briefing by FHI project office staff on arrival | During this meeting with central and district office staff it became apparent that FHI central office has run this project in a centralised manner. During interviews with field coordinators, whenever specific questions were asked, the evaluation team was referred back to FHI central office. It appeared that FHI central office controls details pertaining to budgets and overall work planning and reporting. |

| 22/3 | Doti | - Travel to Doti - Met Community Development Forum (CDF) management team Visit Pachanali Radio Listener’s Group - Visit Gopghat ICC centre with outreach staff | Community Development Forum (CDF) is a not for profit NGO registered in 2052BS and started working with alcohol abuse, women and girl’s trafficking, and literacy promotion and claims to be the first NGO operating in Doti. More recently CDF have assisted PLHA’s to start income generating activities such as through livestock and were able to assist PLHA’s access public funds for development. The evaluation team visited a CDF operated Information and Counselling Centre (ICC) at Gopghat. This ICC is one of five such centres in Doti district operated by CDF and funded by FHI. It was explained that the five centres cover 32 VDC’s and one municipality. The Gopghat centre appeared well equipped with literature, pamphlets, videos, card games and was staffed by 2 apparently knowledgeable counsellors. ICC’s appear to operate as an inbound and outreach education centre. The team went on to visit CDF’s main office where it was discovered that CDF has 10 community mobilisations and 6 outreach workers employed to implement the FHI RAB programme. Functions include community outreach education on HIV/AIDS, personal counselling, referral to VCT services, and organising mobile VCT camps (the latter item outside of RAB). ICC’s also conduct street theatre, ‘pamphleting’, storytelling and games to attract attention in schools and community areas. It was explained that CDF has mounted special events such as world AIDS day and condom day. CDF claim to have reached some 25,000 people over the project period through ICC’s. CDF also supports Doti hospital in referral service which involves providing pre-test counselling, taking blood samples, sending these to laboratory for testing and providing post test counselling. As part of their community intervention, CDF also operates 40 radio listening groups for the Nepali language Desh Pardesh radio programme with one facilitator/community outreach worker per group. RL Groups comprise 20-50 listeners and meet once a week. CDF claim Desh Pardesh reaches across the border to and from India providing a communication channel between husband and wife with positive and supportive messages. Males participated in radio listener’s groups in Mumbai, Delhi and Thane through the RAB project partners in India. Thus, the Nepal groups were mainly women (wives of migrants). Some women interviewed said that they doubt their husbands’ fidelity while in India and that in any case their husbands do not listen to them. Many of the women spoken to were deeply concerned about the danger of HIV transmission. For a few wives involved in the programme they had travelled to India to see their husbands. The ongoing existence of the RLG’s are due to the efforts of trained facilitators in bringing women together. These groups are unlikely to be sustained spontaneously without this kind of input. Furthermore maintenance of a radio and provision of power or batteries is beyond the means of the target audience. In addition CDF operates Community Home Based Care (CHBC) for PLHA’s. They have total of 3 CHBC teams each with three members comprising 2 volunteer PLHA’s and one professional health worker per group who also provides elements of primary health care such as health checks, dispense condoms and some OI medicines. CDF claim to be first organisation to employ PLHA volunteers. This strategy appears to be successful in creating positive role models and in promoting empathy, cohesion and self help among PLHA’s. The CBHC teams also fulfil the vitally important function of adherence support and follow up on drop outs. |
| --- | --- | --- | --- |
| 23/3 | Doti | - Met Community Development Forum (CDF) management team - Meet Doti District Hospital ART Team - Meet Doti DHO, DCC | In a further meeting with CDF it was learned that this NGO was active in facilitating wider community and official responses to the AIDS crisis. CDF has conducted seven district AIDS advisory committee meetings to coordinate medical and community response. One DCC member spoken to reported that he had visited an AIDS affected area in the company of DPHO, LDO and CDO and that this provided a very effective informal channel for communication. It was felt that this kind of first hand experience has helped to advance understanding of the HIV/AIDS problem in the District. It was said that these field trips opened the eyes of the heads of the other organizations. CDF reported several significant challenges that have arisen from this RAB project. The first is the difficulty PLHA experience in getting affordable access to OI medication. The review was told that PLHA frequently present with OIs and often encounter difficulty in getting relevant medicines free from Government run clinics. There was discussion about project continuity arrangements with FHI phasing-out its support in February 2009. It was explained that CDF has been operating five major activities through FHI support. These are; ARV Treatment Centre, Radio listener’s Groups, ICC Centres, Out reach, and Community Home Based Care (CHBC) program, all of which were maintained up to February 2009. Since then agreement has been reached with Global Fund Round 7 to continue some of the above-mentioned activities from April 2009. In addition, the USAID-funded ASHA Project will also support CHBC and care/support for PLHA in Doti through CDF as the Global Fund grant coverage is very low. Concerning institutional capacity building, the evaluation team heard that CDF consider they have been well trained in the areas of documentation, reporting, financial management, and leadership skills. However they felt much less confident about their technical knowledge and skills in field level health care and patient support. The evaluation team moved on to visit Doti District Hospital ART centre. Here it was learned that the ARV treatment centre was initially set up through FHI project funding and is a Government of Nepal official ART site. However the operational and management aspects are running directly under the supervision and support of Doti District Office (DPHO). One, full time, health assistant, medical equipment, supplies including OI medicines are supporting by CDF through FHI funding. The ART centre is currently providing treatment for 124 ARV cases on a regular basis. During the FHI support period a total 298 HIV positive cases were detected out of 1146 tested cases. 105 male, 168 female and 25 children are living with HIV. 9 females and 4 males died during ARV treatment. One client has been lost over the past 3 months. At present 116 PLHA (65 females and 51 males) are taking regular ARV treatment. Out of these 116 ARV cases 25 males and 33 females were transferred in from Mahakali, Assam, Kailali and from India. 26 male and 33 female started ARV from Doti Centre. DPHO claimed that HIV/AIDS is highest in Doti District. Almost 7% of the national ARV treatment cases are managed from Doti District Centre. Throughout the entire country there are only 2,500 PLHA receiving ARV treatment, yet Doti District’s population is under 1% of the total country population. The scenario is considered to be getting worse; HIV/AIDS cases are expected to increase epidemically for many years because of the existing infection level. “However there is optimism that it will eventually decrease in the long run. |

| 23/3 | Doti cont’d | - Meet Doti District Hospital ART Team - Meet Doti DHO, DCC - Travel from Doti to Dhangadi | CDF claimed that FHI’s CHBC program has been a most effective tool for bringing PLHA cases to ICC, VCT, ARV centres. From observation, this appears to be true. CDF also claim to be the only local organization that is working directly with PLHA’s and in the process are providing jobs for 6 PLHA’s. Community based home care is currently operated through teams which consist of two PLHA’s and one ANM. These teams are equipped with a basic kit with medicines and supplies. They provide support for all PLHA at home, teach the PLHA, their family and neighbours about HIV and its care. Many PLHA with whom the evaluation team came into contacted during their field visit repeated similar remarks to the effect that “we could not do anything without the CHBC team. They are like our parents”. They also mentioned their concerns about the FHI project phasing out and the worry this is causing them. Observations at the ARV treatment centre in Doti District Hospital. The clinic room appear to be equipped with the necessary medications and supplies. However, there is no privacy maintained and patients were listening to each others’ communications. Some sense of privacy could easily have been provided within the clinic through a simple curtain. At the time of the evaluation team’s visit the FHI supported full-time Health Assistant was out of town. A nurse in-charge was handling the ART cases on top of her regular work. She was busy maintaining regular cleanliness and supervising linen changes in the inpatient ward while also trying to take care of ARV cases. At the time there were five ARV cases present and all were in a hurry to get their medicines and catch their buses to return home. The duty nurse was hardly able to hand out the medicines owing to time pressure and consequently there was no opportunity to listen their health complaints. Counselling and checking of vital signs was out of question. Hospital staff members were already obviously heavily loaded with their own regular case work. There appears to be negligible support from MOH for this extra workload. DPHO is facing the problems of high turn over of Government appointed staff in the hospital and this also seems to be having a significant impact on the quality services. The lack of free availability of OI medicines appeared to be the main problem affecting PLHAS health. It was also reported that after a lengthy wait the CD4 machine had still not arrived. There was no provision for PMCT management. Staff simply remarked that we are referring all PMCT cases to Mahakali Zonal hospital. However due to transportation costs and other logistical problems it was understood that none of the PMTCT cases referred from Doti had managed to get to the Mahakali Zonal hospital. It was reported that one PMCT case was nevertheless able to go on to deliver a baby. The medical teams and the DDC representative reported that it has been difficult to measure the behavioural changes among the ‘at risk’ population and from their observations few changes been noticed. However they felt that people now seem more able to openly share their knowledge and that they can now talk about condoms in public. It was observed that overt signs of social discrimination and stigma are decreasing to the extent that people no longer make rude comments about PLHA;’s in their face, nevertheless backbiting is a chronic problem. All implementing agencies indicated that they have good relations with DAAC. CDF reported that they are able to keep close coordination with other Government officials, political leaders, and local bodies. The DPHO, Mr. Mahendra, has been very supportive and is considered to be popular in the district. |
| --- | --- | --- | --- |

| 24/3 | Kanchanpur | - Visit NNSWA – ART & VCT team - Meeting with Mahakali zonal hospital medical team - Visit Malakheti VCT centre - Visit Red Cross PLHA support group | Visit to Mahakali Zonal Hospital and NNSWA office in Kanchanpur. Mahakali zonal hospital has been running ART services since May 2006 . VCT and ART services are also being provided. Presently VCT services are being provided for 230 and a total of 141 cases are receiving pre ART treatment. Among these 141 cases, 54 are male, 65 female and 8 male children and 14 female children. Out of a total of 35 PLHA, 17 males, and 18 females, including 1 male child and 2 female children are receiving ARV treatment. Two females and one male died during ART. ART services are being run under the direct supervision of Mahakali zonal hospital by one full time Nurse/Counsellor, a medical team from NNSWA and a visiting Doctor. The medical team includes a focal person who is in charge of PMTCT care. In Mahakali Zonal Hospital privacy has also not been maintained at all in consultation rooms. Many patients were seen queuing up inside the room; however in the Doctor’s room only 2-3 PLHA’s were queuing up. The evaluation team observed PLHA blood samples being drawn outside the consultation/counselling room in conditions of poor hygiene, with flying dust. Further a laboratory technician was seen drawing blood from two successive PLHA patients while using the same pair of gloves. When asked about universal precautions they seemed to be aware of this discipline but nobody answered our question. The medical superintendent and medical team assured us they were willing to provide the best possible care for all patients in the clinic and hospital but the additional workload with very limited manpower has been extremely difficult to manage. The medical superintendent mentioned that the routine work to run a 50 bed hospital, high pressure of delivery cases, VCT, PMTCT, ART,EID, all laboratory tests have been too much to handle. He also mentioned that there are only four doctors on duty whereas in the official organisation chart there are 18 Doctor posts. A maternity ward charge nurse using a back brace to help her with the strain of lifting was working at the time of our evaluation visit. The medical team further mentioned that they don’t get sufficient supply of OI medicines, PMTCT kits, Lukun tablets etc. The succinct comment was that to run all of this as a regular program will be a big challenge without support from NCASC, FHI and other organizations. ‘’We want to provide best care, but need enough trained manpower, regular and enough supplies and regular in service and refresher training.” |
| --- | --- | --- | --- |

| 25/3 | Kailali District | - Visit Seti Zonal hospital ART centre – meet NKP team, ART and VCT teams - Meeting with medical superintendent and medical staff - Meeting with chairperson Zonal hospital management committee | Visit Seti Zonal Hospital and partner organization Nava Kiran Plus The evaluation team held discussions and observations at Seti Zonal hospital. As one of the outputs, the RAB project has established a care and treatment service for HIV+ Nepali migrants and their families in Dhangadi. A special ward has been allocated in the indoor department of Seti Zonal hospital and admitted HIV+ patients are being treated by trained medical officers and nurses. The team was able to witness the morning round being conducting by the medical team comprising three medical doctors and four nurses. It was noted that the medical team were discussing the case of one patient who needed to be referred for second line treatment in Kathmandu However it appeared that routine para-nursing support was being provided mostly by members of the voluntary NGO Nava Kiran Plus (NKP). It was explained to the review team by NKP members that this was necessary owing to continuing stigmatisation of HIV patients resulting in insufficiency of nursing services by hospital staff. However according to the medical in charge it has been very difficult to manage the extra cases with the limited number of staff. They were also receiving more delivery cases after the provision of free delivery care services. There is no extra budget and manpower for extra work. The team then moved to the nearby VCT and ART centre. This is housed in a separate two level building, on hospital premises, that was renovated by FHI to make it a suitable amenity for providing OPD, counselling and all other OPD based services. The evaluation team observed all the intake process at the clinic, In all there was a total of 8 staff members including; two counsellors, two nurses, two Lab. assistants, and 1 doctor. A group of 6 Nava Kiran internally trained medical assistants were also helping at the clinic. There were 48 patients registered through to 2pm. The NKP volunteers were seen handling patients with care and love and escorting them to the registration department consisting of a small corner behind a curtain, Patient history details were taken, the usual weight and vital signs checked, then the patient was accompanied to see the Doctor and counsellor if necessary. The Dr‘s office seemed quite large for a consultation room. After the Dr’s consultation the patient was send to collect their medicines. The dispensary pharmacist was quite clear in giving her instructions concerning medicines, timings and any other side effects that can be expected. The evaluation team also observed during the registration of children, the use of a small hand tape to measure the child’s height where they could easily have fixed a standard height chart on the wall. There was little sign of any nutritional messages such as posters on walls. FHI has been providing OPD medical staff salary and OI medicines which is a great help. The review team also observed the laboratory which was well equipped with a CD4 count machine and basic investigation facilities. All equipment was found to be functional, logistics and supplies were adequate and the team was told that supplies are generally received on time. While at the Laboratory, the team observed two young children giving a blood sample and, as in Mahakali, the Lab. Tech used same pair of globes when handling each child’s sample. When we asked about the Universal precaution he seems to know, did we didn’t not get chance to hear his answer. Overall the OPD staff members were very friendly towards their patients and the counselling department was also set up in a friendly manner where both parties could sit at the same level. It was quite impressive to see the friendly manner of putting patients at the same level. Evaluation team met four returned migrants all of whom attempted to use, while in India the standard ARV treatment referral identification card carried by all Nepali ARV therapy patients. Two of them stated that, while in India, they received ARV medicines from Delhi based Sathi’s free of charge and also contributed some of their time as paid workers for the same organisation, where they were able to help many Nepali PLHA’s. |
| --- | --- | --- | --- |
| 25/3 | Kailali District | - Visit Seti Zonal hospital ART centre – meet NKP team, ART and VCT teams ……….Continued | Another returned migrant who the team met at Seti zonal hospital ART centre had a different experience while in India. He found it extremely difficult to obtain free services and medicines using his Nepal issued referral card at locations in Maharashtra. In frustration he went to a private pharmacy and purchased what he though were the correct items. The patient reported that this cost him INR 3,000/- per month and that his health continued to deteriorate to the point that he was forced to return to Nepal. A fourth interviewee explained that it was so difficult to obtain free services in India that she was forced to resort to getting her husband to send her medicines from Seti ART centre every three months. Visit to Nava Kiran Plus in evening NKP was established in December 2006 in Dhangadi, Kailali to support and strengthen the quality of PLHA’s life. From the beginning of the project the following services have been providing from Kailali District Branch; Treatment, care and support, advocacy, awareness and prevention, capacity building for PLHA, adherence counselling, hospital volunteering service, skill building training and treatment literacy. FHI has been supporting NKP over the last 14 Months. FHI support is mainly for staff salary, office equipment, supplies, and technical support in both medical and administration. NKP’s 5 staff members attended three days training twice during the 14.month period. During a tour and discussion with NKP employees, it was observed that the NKP hostel was packed mainly on Wednesdays. Wednesday is CD4 day in Seti Zonal hospital and NKP staff reported sometimes they could not accommodate the PLHA in their total of 30 beds. They tried to accommodate everybody who comes to the hostel. Most PLHA’s are poor and can not afford to stay in hotels. NKP staff put mats and mattresses on the floor and provide the best comfort they can. NKP staff expressed that they work hard days and nights from their heart. The evaluation team members were all impressed with staffs empathy towards PLHA’s. It was also noticed that NKP’s staff were helping out in the ART clinic and in the Hospital. However it seems that a little training on nutrition would be great benefit to the PLHA groups since good nutrition is known to play an important role in sustaining ARV therapy. |

| 26/3 | Kailali | - Visit Red Cross office Kailali for executive interviews then visit Red cross Baliya centre and conduct – group discussion with 50 volunteers & 40 PLHA’s and also FHI funded workers from NSARC, NKP and Red Cross | The evaluation team met Nepal Red Cross Society (NRS) Kailai District Board Director, board members and FHI funded staff. According to the president, Kailali branch Red Cross society is the biggest organization in the district conducting HIV awareness and prevention programmes and also providing ARV therapy services. In Kailali District there are forty two VDCS, two municipalities, one Zonal hospital, six Primary Health care centres, and thirty sub health posts. NRS have been working in ten VDCs with FHI’s financial support in the areas of; outreach, education, community mobilization, CHBC program, and radio listening program, and blood transfusion services. Fifty eight full time and part time employees were working until February 2009. As at the time of the meeting, they were still not certain whether any part of this programme will continue. They were verbally told by some of FHI’s senior officers that the entire program will continue from April 2009 except for the Radio listener’s activities. All employees are waiting to hear news from FHI. It was expressed that all field workers are extremely dedicated and very much attached to their PLHA group in all aspects even though at times they feel they are stretched beyond their capacity. They work day and night with communities to meet their physical, emotional, spiritual and social needs. The NRS president mentioned to us that this FHI project was an eye opener for them, yet nobody realized that this project would come to phase out so quickly. In the Red Cross executive group meeting an NRS board director requested the SWC representative, on the evaluation team, to urge SWC to develop a policy for I/NGO’s. It was suggested that individual INGO’s should not attempt to do everything and spread themselves too thinly, rather they should be encouraged to contribute their unique skills and strengths to a comprehensive development programme for particular areas or regions. He went on to explain that Poverty is the underlying issue which manifests in a multitude of social problems including HIV/AIDS. With the support of FHI, NRS has been supporting PLHA’s for supplies, blood transfusion, travel expenses and the cost of laboratory tests. NRS itself is a purely voluntary organization. Therefore there is no way NRS will be able to support PLHA’s when FHI withdraws. NRS does not have sufficient budget to cover these cost. Red Cross members also expressed their concern about discrimination and stigmatisation. It was explained that ‘Changing behaviour is not a one day process; it is a long term process. People have been practicing certain behaviour for generations. Social discrimination and stigma have not changed in practice. So many PLHA’s children are out of school. In a few schools parents took out their children away when they knew PLHA students were in that school.’ In a further group discussions with some 40 PLHA’s it was learned that almost all the male population of the area migrates to India for work and that Nepalese migrants are concentrated in specific location in India commonly including Delhi, Bombay and Pune in Maharastra, Punjab, and Gujarat. Investigation has indicated the most likely and common cause of HIV infection is sexual activity with sex workers. It was stated that most of the men remain in India for about 4- 5 years and it is usual for male migrants to have their work positions terminated once their employer discovers that they are HIV positive. By the time HIV infected migrants return home, they are usually sick and are unlikely to have received treatment in India through their employers and besides had no idea about systems for distribution of medicine in India. One unique case of one male individual who is under ARV treatment was cited. He obtained a stock of medicine from Dhangadi Hospital to cover three months as a special case and went back to India for work. |
| --- | --- | --- | --- |
| 26/3 | Kailali | - Visit Red Cross office Baliya – group discussion with 50 volunteers & 40 PLHA’s and also FHI funded workers from NSARC, NKP and Red Cross | In another case the wife of a PLHA was sending ART medicines to her husband in India and that continuity is informally supported by letter and telephone. In reply to a question concerning non-collection of medicines, Red Cross staff confirmed that such incidents are closely monitored and medicines are delivered if necessary through the migrant’s wife and other family members. The review team sought information about the frequency of CD4 testing for PLHA’s and were told that the counting test is done on a 6 monthly basis with some deviation of up to 6 – 10 days . This delay is mainly due to bandh and lack of funds with patients. However on the basis of a show of hands, at least 10 of those PLHA’s present indicated that they had not had a CD4 test in the last 8-10 months. In a related topic evaluation team member Dr. Pradhan informed the meeting that the Government is planning to provide monthly nourishment supplements worth Rs1,000 for ART patients. He enquired whether those present would like to have food supplement or free transportation and CD4 testing. The unanimous reply was they wanted both but if having to make a choice would prefer to have free treatment. Following on here were two further group meetings in which swot analysis on RAB project was conducted |
| 26/3 | Kailali Continued | - Visit Nepal STD and AIDS research centre (NSARC) Attariya clinic - Return to Dhangadi | Visit Nepal STD and AIDS Research Centre (N’SARC) N’SARC Kailali branch advised that this is an NGO established in 1983 and has been working in the area of HIV/AIDS and STI prevention and care in the Mid and Far western regions of Nepal over the past 10 years. They are providing clinical services including STI, VCT, and HIV care and support. In this area. They went on to describe activities that have been conducted with financial support from FHI in the period December 2006 through to February 2009. During this period, a total of 3,331 VCT tests were completed out of which 137 cases were found HIV positive. In the same period 3153 STI tests were conducted with a total of 954 STI’s diagnosed and 925 were treated of which 44 were RPR reactive. A total of 333 new EPC clients were found out of 828 client visits and 153 cases received OI treatment. N’SARC advised that they also conducted regular PLHA support group meetings, skill building meetings along with special small income generation training to support the PLHA. N’SARC acknowledged that FHI funded 9 staff member’s salaries, VCT kits, laboratory regents, O/I medicines, computer, fax and office equipment and supplies. All the above mentioned activities and programs have been conducting over some 10 years; hence it is not possible to give all the credit to recent FHI funding since much of their organisational capacity has been established in earlier period. Nevertheless N’SARC has made impressive achievements during the current project phase. It was observed that the Clinic in charge has extensive knowledge in many aspects of STI/HIV/AIDS but has not had the opportunity to attend training in Uterus prolepses. It was also discovered that the West and Far West region have a higher rate of uterus prolepses than the national average. Since this is an aspect of reproductive health closely related to STI testing and treatment it is suggested that it might be best to train all medical staffs in this serious health issue. The only other serious observation concerned NSARC’s apparent non-compliance with quality assurance standards for Lab. testing conducted at this facility. |
| 27/3 | Dhangadi | - Final team review meeting - Return to Kathmandu |  |

3.2 In-Depth Interview Questionnaire Results

3.2.1 Part A: Managerial – Interviews with Senior Members of Implementing Agencies

Senior members of community based organisations and hospitals involved in the RAB project were interviewed at Doti, Seti, Mahakali, and Kathmandu. These interviews made use of 53 questions shown in the questionnaire that can be found in the appendix. Ten interviews were completed. Highlights include the following items:

- Q.1 – Concerning the project goal and objectives responses fell into the following categories and were mentioned the indicated order of frequency:

- 9 x HIV Treatment & Care

- 8 x HIV Transmission prevention

- 7 x HIV Awareness

This indicates that perceptions of the projects purpose were fairly evenly distributed between treatment and prevention issues

- Q.6 – Concerning the most effective activities the respondents nominated areas including direct presentations and voluntary community service:

- HIV awareness in schools

- Video show

- Story telling in local common languages

- CHBC

- ICC

- HIV/Aids prevention in Doti

- Q.8 – Asked to nominate other activities that might have been more effective respondents mentioned the possibilities:

- Video and radio programmes in local common languages

- More VCT services

- Income generation programmes

- Assistance for PLHA’s with basic needs when collecting medicines

- Q.9 – Concerning identification of the targets for this project respondents were nearly unanimous in mentioning:

- Male migrants and their families

- Q. 10 – Concerning the degree to which this group had been reached the respondents’ opinion was divided between high and medium to low

- Q.11 – The respondents cited factors for and against project sustainability. Factors in favour included institutional capacity building and growing HIV awareness, factors against included the ongoing dependency of PLHA’s

- Q.12 – Asked how the project had changed what their organisation does, respondents mentioned improved capacity in documentation and reporting. The advent of the CHBC programme was also mentioned

- Q.13/14 – Concerning project uptake respondents indicated the project was slow to get started partly as a result of stigma and discrimination but that the introduction of street theatre helped to break down barriers

- Q.16/17/18 – Respondents mentioned many outside organisations with which they had to coordinate and felt that stronger coordination was needed and that joint project monitoring would be a good more in this direction

- Q.19 – Respondents indicated that one of their greatest concerns about the project was the need for much greater local involvement at every stage of the design process to ensure the programme meets its targets. They also felt that poverty alleviation should be accorded a high priority since it is the main underlying cause of social ills

- Q.20/21 – Respondents identified key areas of learning from the project included:

- That it is possible to survive HIV

- The success of the CHBC programme and  that PLHA’s can take care of themselves

- NGO organisations must be responsible for their own sustainability

- Education and media presentation materials need to be based in the local common language and cultural idiom

- There needs to be better management coordination and networking

- Q.22 – Respondents were divided as to the level of local awareness about this project but the overall consensus was that it was not high

- Q.25/26/27 – Respondents were able to clearly identify demographic factors concerning the migrants and the source communities from which they typically originate. These are:

- Mostly married and unmarried men

- Mostly lower castes (particularly Dalit) owing to poverty but including a significant proportion of Chhetri caste

- Common originating localities include: Aacham, Baitadi, Bajang, Doti, East Doti, Daldeldhura, and Kanchanpur

- Q.29/31 – Asked about how effectively the project reached these communities the respondents felt it was generally good owing to the efforts of ICC and VCT programmes but that overall consensus was that the impact was not high and that general awareness was still low to medium.

- Q.32 – Respondents assessed the general level of knowledge in the community about HIV and how it can be transmitted as only “A Little” or “Some”

- Q.33 – Respondents were unsure if there was strong evidence of risk behaviour change however they generally felt that it was now more possible for people to talk openly about HIV, sex and condoms. In a further anecdotal account it was told that some women were sufficiently empowered to  insist that their husbands submit to VCT on their return from India

- Q.34/35/36/37 – Respondents generally were happy with the resources they had received including the amount, quality and timeliness. The most frequently mentioned items were training, ICE materials, office equipment and staff salaries. Donors mentioned included FHI and UNDP

- Q.38 – All respondents agreed  that they could do more work if they had additional resources

- Q.39 – All respondents indicated that they had gained skills and capabilities through this project, the areas most mentioned included: Leadership skills, documentation, proposal writing and reporting

- Q.40/41/42 – Respondents generally perceived the area of reporting, measurements and controls to be bound up with monthly supervision from various organisations including their board members. They felt however that information collection, analysis and reporting could be improved through further training of lower and mid level staff and through greater participation by FHI central office in regular M&E activities

- Q.43 – Asked to cite a remarkable success story associated with this project, the interviewers heard that:

- Doti HIV/AIDS awareness programme had been a great success identifying many HIV+’s

- CHBC had exceeded expectations

- Q.47 – No significant confidentiality, moral or ethical concerns were raised however a counsellor told the evaluation interviewer that from their experience there can be no doubting the reality that male migrant workers generally use prostitutes while in India

- Q.48 – Asked what were the underlying motivations for the project, all respondents confirmed all the following multiple choice items:

- Establish approaches and methods to make migration safer

- Identify and treat maximum number of  HIV/AIDS/STI cases

- Increase numbers using ART

- Minimize transmission of HIV

In addition several respondents added items to do with care for PLHA’s and helping them to live better lived with reduced stigma and discrimination

- Q.49 – Asked if it was possible to measure effectiveness in reducing HIV transmission the respondents provided a range of answers

- Impossible

- Possible with a regular survey

- Possible if have record of all VCT camps and records from all health and sub-health posts

- Q.50 – Asked if there should be some official control over migration involving testing, all respondents stressed the importance of pre and post migration testing and agreed that mass testing would be of immense value in stemming HIV transmission from India

- Q.51/52/53 – Senior members of all participating organisations when questioned confirmed that they were selected because of their past experience in this area, that they would wish to continue this work under a new project but that they would need additional resources including staff, materials, skills training, VCT centres, CD4 testing facilities, and medicines

- Q.54 – In closing one or two respondents remarked that they would like to see the Government play a greater role in this area and not simply rely on INGO’s

3.2.2 Part B: Interviews with Clinicians and Laboratory Staff

Medical, nursing and laboratory staff members involved with VCT/ART related services were interviewed at Mahakali hospital, Seti Zonal hospital, Doti district hospital, Kailali PHC, and N’SARC Attariya clinic. These interviews made use of 18 questions shown in the attached questionnaire.

Overall results can be summarised as follows:

- Some respondents felt that their technical training was insufficient

- Most respondents were comfortable with their training for patient interviewing and counselling

- Respondents reported that a variety of equipment was provided ranging from fridges to microscopes, air conditioners centrifuges and autoclaves etc. was supplied for this project but not exclusively from FHI, Staff reported that the equipment was in good working order and were willing to show the equipment to the review staff

- All respondents reported that consumable supplies were provided, most commonly testing kits but also reagents, gloves, microscope slides etc. However there were concerns about timeliness of deliveries, long lead times from ordering and resulting periodic shortages

- Most clinical respondents reported that the project had a medium to high impact on their workload in both laboratory and clinical services where an assistant was often needed

- Clinicians reported that while patients were fairly regular with ARV therapy they were not always so regular with medicines prescribed for OI conditions

- Clinicians most frequently expressed a need for basic and refresher training in testing and related procedures

- Clinicians were mostly aware of the need for PMTCT for pregnant women however these services were only available at Mahakali Zonal hospital

Other observations:

- The evaluation team noted that Clinicians taking blood samples were not seen to change gloves between successive patients

- It was understood that In Doti support for the many on going   activities enabled under this project will be take over by Global Fund. Consequently the staff   were somewhat relaxed about sustainability.

- At Mahakali and Seti the story was very different from Doti with clinicians and senior management all expressing grave concern about the capacity to sustain workload, supplies and particularly OI related drugs on termination of the project

- While there was evidence of considerable technical capacity having been built at the five clinical sites visited the evaluation team hopes the sustainability of VCT and ART services at the end of this project particularly at Seti and Mahakali.

- RAB HIV/AIDS initiative is not well integrated into general reproductive health services. While clinicians are adequately trained in STI/HIV they have little if any training areas such uterus prolepses which is frequently presented

3.2.3 Part C & D: Interviews with Patients at Clinics and at Home

Patients were interviewed at Doti district hospital, Mahakali hospital, and Seti Zonal hospital. A number of home based patients were also interviewed. These interviews made use of 19-20 questions shown in the attached questionnaire formats for in and out patients.

Overall results can be summarised as follows:

- All patients were fully aware of their health condition and familiar with the various medications and the importance of adherence and particular timing. Many reported minute details of their health conditions including kidney stones etc. Respondents reported being on ART for between 6months and 3 years and most recognised that therapy would be needed for all of their life span. Most respondents indicated that they were referred by NGO outreach staff. Some however identified their family members as the referring agent.

- Most respondents understood how HIV is transmitted and how further transmission can be prevented

- Respondents reported that their families were aware of everything to do with their health condition but not their neighbours indicating that social stigma persists. This includes some rude remarks about receiving transport subsidies and even extends to outright discrimination concerning enrolment of HIV+ children in schools and use of communal bathing facilities

- About half of the respondents reported receiving healthy living advice but few considered they had sufficient means for more than a very meagre diet.

- Half of the respondents depended on labour for their livelihood a few had land, animals or some other income source such as a shop. However it was observed that the majority of PLHA’s were living in a degree of poverty

- Generally respondents felt positive about their treatment and expectations for an extended lifespan. Those receiving treatment at the clinic were happy with the way they were treated and were quite happy with transit accommodation, Those being treated at home were also generally happy with their treatment and monthly health worker visits

- While all respondents reported no charge for ART drugs the same was not always true for OI therapies where often only some of the prescribed medicines were provided free of charge. Even transportation costs were not uniformly reimbursed. The NGO staff confirmed that some form of means testing was being applied

- All respondents reported having had some contact with community based organisations at least in the initial stages of their treatment and are generally positive

- The vast majority of respondents were female and most reported that their husbands were away working in India and in some cases were also on ART therapy.

- All respondents had either themselves or their family members been abroad to India. In most cases male members

- All respondents indicated that they desired some form of Government support for food security, education of children, other medical conditions or continuation of the project

Other observations:

- The evaluation team noted that almost all patients appeared needy and either malnourished, under weight and/or anaemic especially affected children

Issues Identified:

- The overwhelming issue arising from patient interviews appeared to be the effects of poverty particularly malnutrition and the clear need for special nutritional support for many patients.

- Other forms of deprivation were evident apparently arising from stigmatisation resulting in unequal access to community resources particularly public bathing water and education for children.

3.2.4 Part F: Interviews with Project Owners

These interviews made use of five questions shown in the attached questionnaire. The intention of the interview was to seek out project owner’s perspectives on significant overarching issues including; HIV prevalence among migrant workers, the scale of worker migration and likely scale of the vector driving the present epidemic, methods that might be incorporated in the project to assess effectiveness of prevention activities and the relative weighting of resources dedicated to prevention versus treatment and care. As it happened no interview was conducted and only a single written response was made available from FHI. While the lack of a personal interview was disappointing, it is felt that the responses were helpful to this evaluation in illuminating the approaches adopted by project designers, and are summarised here.

- In the first interview question, asked if the crude quotient of 600 HIV positives out of 8,000 VCT tests might be a representative sample and a fair indication of the real infection rate among male Nepalese migrant workers to India.  The written response was ‘No’ and the following comment offered.

‘VCT data are biased by default because people who come in for testing voluntarily have already perceived themselves at risk for HIV infection. Therefore, using VCT data to determine prevalence rate would lead to an overestimate in most cases.

In RAB project area IBBS among male labor migrants to India has shown around 1% HIV prevalence in 2008. Among those who have worked in Mumbai or who had sexual contact with FSW’s in India the rate was about 5% HIV prevalence.’

- The second question drew attention to the project background narrative where it was cited that male migrants to India number in the range 6,00,000 to 12,00,000 and that the annual migration to India may be responsible for 30-50% of the current HIV burden in Nepal. The interview question sought details on the source of this information and whether it is possible to be more precise in the estimates. The following written comment was provided:

‘Source of information for estimated number of migrants to India is National Estimates of HIV infections, Nepal 2005 – report Published by National Centre for AIDS and STD Control.

2007 estimates from the National Estimates of HIV Infections, Nepal 2007 are 660,000 to 1,400,000’

- The third question sought to connect infection rates with estimates of migrant numbers and draw out the respondent’s views on the number of HIV carriers entering Nepal each year. The following response was given:

‘To estimate the HIV infections among the migrants we cannot use the same prevalence rate to migrants from all parts of the country. About 1% HIV is in the Far Western region. In other regions prevalence is lower. National Estimates of HIV infections, Nepal 2007 report gives these estimates.’

- In the fourth interview question, asked whether any particular factors or methods had been incorporated into the project design that might allow the managers to demonstrate or claim to measure effectiveness in reducing HIV transmission, the following comment was offered:

‘To measure reduction in HIV transmission we would need to look at HIV incidence rates and we do not have studies to do that. We can look at trends in HIV prevalence rates over time and we do that through the IBBS. However our project is only one of many projects in the Far West and so we would not be able to completely attribute reductions in HIV transmission only to RAB.’

- The fifth and final question quoted the old adage that “Prevention is better than Cure” and asked; what was the approximate proportion of RAB project resources that were committed to prevention versus treatment, the reason for the relative allocation and whether there should have been a greater emphasis on prevention. The following written response was given:

‘In this project 34% is spent on prevention activities and 66% on care, support and treatment.

Due to specific nature of the project, RAB had given priority on care, support and treatment component. Please note that USAID supported ASHA Project also implemented in the far west region and have also dedicated resources to HIV prevention activities’

  - Focus Group Meetings

The results of the focus group meetings are shown below in four parts:

  - Group Discussion – Group  No.1 – SWOT analyses on RAB conducted in a mixed group comprising members of implementing NGO agencies

  - Group Discussion – Group No. 2 – SWOT analyses on RAB conducted in a mixed group comprising members of implementing NGO agencies

  - Group Discussion – Group No. 3 – Transcript of a group meeting arranged with some 40 PLHA’s in the company of their Red Cross support workers. This interview was conducted at Baliya Red Cross Office on 26 March

  - A Success Story contributed by focus group no.1

  - Group Discussion – Group No.1

Conducted among Red Cross/NKP/N’SARC Staff
Dhangadhi – 26 March 2009

Subject: SWOT analysis on the RAB project

Strengths:

- The project has established good relations among village communities

- Public awareness about HIV/AIDS has been increased

- HIV infected people gained access to medical facilities and treatment

- VCT services have been made available

- Public awareness about HIV/AIDS has increased through the establishment of home treatment services

- HIV/AIDS related public awareness among various groups in community has helped HIV positive people can admit their problem openly

- Use of condoms is increasing somewhat

- Through condom day and AIDS day the common people are gaining information on HIV/AIDS, STI and condom use

- Discussion about HIV/AIDS in various community groups has helped to reduce HIV infections

- Through radio listener’s groups a voluntary savings and credit scheme has started among the HIV/AIDS cases

Weaknesses:

- The programme period was very short

- There was very limited training and facilities for field workers

- The community events including video show and PGD interaction did not adequately reach target groups

- There was insufficient IEC information materials

- This programme should have been operated across the entire district not just 10 VDC’s

Challenges:

- Many among the target group are not interested to receive information about HIV/AIDS

- People often become angry when we talk about condom use

- Males and females resist coming together for radio listening groups

Suggestions:

- Programme should be launched in the entire district

- There should be enough IEC materials

- This programme should continue for longer period

3.3.2 Group Discussion – Group No.2

Conducted among Red Cross/NKP/N’SARC Staff
Dhangadhi – 26 March 2009

Subject: SWOT analysis on the RAB project

Strengths:

- PLHA people are becoming more open about HIV these days

- Instances of discrimination are becoming less frequent

- Rural people have gained opportunities to know more about HIV/AIDS

- ART is easily available

- Free STI & HIV treatment and counselling is available

- People who are working abroad and their families have learned about HIV/AIDS and they also learned the importance of counselling and blood testing

- HIV infected people have learned that ART should be taken regularly and they understand that HIV is not necessarily a deadly disease

- Women sex workers and their customers have learned more about STI & HIV and the need for testing and treatment

- Public awareness is spreading that besides one’s life partner sexual contact should be prohibited or condom should be used systematically

- They have understood or learned to check HIV before returning home from India or before marriage

- Poor people who are coming to take ART from faraway places are give bus fares

- HIV infected people have got facilities for Transit Home

Weaknesses:

- This programme was implemented for a very short time

- The programme is operating only in limited areas

- There is no efficient training

- Salary and allowances are less than the value of the work that is being done by field staff and volunteers

Opportunities:

- Simple or middle educated people can also be provided work

- This programme can provide job opportunities for many people

- Uneducated people and poor persons from villages have been getting home health facilities and they are learning about HIV and sexually transmitted diseases in their own home without the need to visit a clinic

- HIV infected people can get medicine facilities in their own home

Threats:

- If the present FHI programme finishes then people will be without of services.  This is the biggest challenge

- Presently the programme covers only 10 VDC’s. If coverage is not extended across the entire district then all people in the district will eventually suffer and many may die from HIV

3.3.3 Group Discussion – Group No.3

Conducted among some 40 PLHA’s and Red Cross Staff
Baliya – Dhangadhi – 26 March 2009

In an informally arranged focus discussions with some 40 PLHA’s it was learned that almost all the male population of the area migrates to India for work and that Nepalese migrants are concentrated in highly specific locations in India; commonly including Delhi, Bombay and Pune in Maharastra, Punjab, and Gujarat.

It was mentioned that investigation has indicated the most likely and common cause of HIV infection is sexual activity with sex workers. Sharing of razor blades is a secondary possibility since many migrants use shared accommodation facilities.

It was stated that most of the men remain in India for about 4- 5 years and it is usual for male migrants to have their work positions terminated once their employer discovers that they are HIV positive. By the time HIV infected migrants return home, they are usually sick and are unlikely to have received treatment in India through their employers and besides had no idea about systems for distribution of medicine in India.

One unique case of one male individual who is under ARV treatment was cited. He obtained a stock of medicine from Dhangadi Hospital to cover three months as a special case and went back to India for work, In another case the wife of a PLHA was sending ART medicines to her husband in India and that continuity is informally supported by letter and telephone. In reply to a question concerning non-collection of medicines, Red Cross staff confirmed that such incidents are closely monitored and medicines are delivered if necessary through the migrant’s wife and other family members.

The review team sought information about the frequency of CD4 testing for PLHA’s and were told that the counting test is done on a 6 monthly basis with some deviation of up to 6 – 10 days. This delay is mainly due to bandh and lack of funds with patients.

However on the basis of a show of hands, at least 10 of those PLHA’s present indicated that they had not had a CD4 test in the last 8-10 months.

In a related topic evaluation team member Dr. Pradhan informed the meeting that the Government is planning to provide monthly nourishment supplements worth Rs1,000 for ART patients. He enquired whether those present would like to have food supplement or free transportation and CD4 testing. The unanimous reply was they wanted both but if having to make a choice would prefer to have free treatment.

3.3.4 Success Story

Contributed by focus group no.1

Ram, who lives in Balia VDC ward no.6 and Sunita who lives in Balia VDC ward no.8 were betrothed to be married by their parents. A member of FHI RAB project staff met Ram, who had recently returned from India where he had been working, explained the dangers of HIV and convinced him to submit to an HIV test. On testing HIV positive Ram recognised that the marriage could not go ahead and explained the difficulty to both his parents and to the girl’s family, whereupon the marriage arrangement was broken off.

This was considered a major success story since the groom had earned considerable money in India and was considered highly eligible. News of the breaking off of the marriage arrangement and the reason for it, spread rapidly in the community and has helped to increase awareness of the dangers of HIV/AIDS.

Note: names were changed to protect identities

3.4   Personal Profiles – Mini Case Studies

Introduction:

The evaluation team have prepared three mini case studies providing personal profiles of selected individuals in the project area who are living with HIV/AIDS. All agreed to share some of their experience and were interviewed as part of this evaluation. Two of the profiles highlight issues connected with the transmission of HIV, from India into home communities, by migrant workers, the consequences and the victim’s and their families’ responses to this crisis.  A third profile concerns a young man who contracted HIV through intravenous drug abuse and who has successfully reconstructed his life as a community service worker providing personal care support and advocacy for PLHA’s.

3.4.1 Case Study No.1

Sushila
Interviewed at – Malakheti – March 2009

Sushila

Sushila, a 30 year old mother of three children works many hours to support PLHA’s. She goes out of her way to help them. Her bicycle runs up and down to the market, hospital and to PLHA’s homes. Sushila told me that the energy and power she feels increases whenever she thinks about these people suffering from HIV/AIDS and when she feels their pain. “I am also a PLHA” she tells me. “I have been taking ARV for the past two-and-a-half years. I saw many people lose their lives before we knew about ARV treatment. I now tell everyone with 100% confidence that you can live at least 25 years if you take ARV treatment regularly. But in reality who knows what will be the lifespan of a PLHA?”

“Sushila tells me that in her village PLHA’s are now able to form and run enterprises such as the ‘Malakheti Cooperative Group’ which has 120 members. Sushila goes on to explain that these are mostly women who have become empowered and have even been known to lock-up the VDC office demanding special support for PLHA groups. Well, Sushila smiles, “the VDC allocated 15,000 rupees for PLHA’s in Malakheti VDC.” Sushila also tells me about a nearby village where PLHA’s were not able to touch water resources, touch food in communal meals, nor able to attend social gatherings.

More relaxed now, Sushila starts to tell me about her past. “It took me three years to get enough courage and even family permission to go for VCT. When I heard that I had HIV I felt like I was already dead. Then they started me on ARV medicines and I knew what it really felt like to be dying, the reaction of my body was so horrible!  Really it was my feelings of shame and my fear that was killing me and eventually I managed to overcome these dreadful feelings and realise that I could survive and make a life for myself too. Now I am an employee of Nepal Red Cross through this project. I love my work but am always worried how long the job will last.”

3.4.2 Case Study No.2

Mrs Devi Singh
Interviewed at – Doti – March 2009

Mrs Rani Singh and her son

Mrs Devi Singh, 42 years of age, opened her mouth after swallowing her tears. “My husband died in India 10 years ago leaving behind four children aged 6, 4, 2 years and a new born baby. I did not know what took my husband’s life but now I understand it was HIV/AIDS”. Having not enough land for adequate food crops Mrs Singh has to earn enough every day for a little grain to feed the children, by doing labouring work. “I was getting weaker and sick, I was having heavy white vaginal discharge and a burning pain in my back and this limited my ability to work”, says Mrs Singh.

“Eventually I was taken to Silgadi hospital, I could not walk properly, and it took me three days to get there. But nothing really helped; I was getting worse and weaker. Then one and a half years ago my neighbour told me to go to Doti hospital for treatment. Again I could hardly walk and it took two days to get here. They told me I have HIV/AIDS and that I need to take medicines all the time. I have been managing to come here and take their medicines for me and my son. I live very far from the hospital; it takes us two days just to get to Doti hospital.

We used to get transit home facilities for a few days but now nothing. By the time we get here we are exhausted yet we can’t afford to buy food. My whole body and especially my joints hurt, and my face is puffed. Back at home, people in my village say I have put on weight and that I come to hospital to receive money. After I return they demand to know how much money I was given. They say I have become clever and use lots of sarcastic words and talk behind my back. Mostly nothing is said directly but it shows on their faces and they avoid our presence at feasts and festivals.

I didn’t do anything wrong, why do I have to go through this. All my children are worried about my health. My three older children don’t have HIV but this young one has got it. The oldest, 16 year-old, son married recently and went to India with his wife and younger brother. They don’t like to be there; the job they are getting is very hard and dangerous and they make very little money. We still owe 17,000 rupees borrowed for my son’s wedding and to send them to India.

I was told from this office a long time ago they will give me assistance to open a small shop, but nothing has happening. My sons and daughter-in-law want to move somewhere and run the shop with me. I am living on hope. I want to see this younger boy go to school. My heart burns to send my children away, they will do anything for survival in this place.”

3.4.3 Case Study No.3

Shyam
Interviewed at – Kailali – March 2009

Shyam
showing his medicine cabinet at NKP

I met Shyam at the Nava Kiran Plus office and clinic in Kailali where he was taking care of a group of ARV patients staying in the transit hostel while waiting for treatment and recovery time. I was surprised to see a sophisticated and cosmopolitan young man in this backward rural area. He explained he and his crew came here from Patan in the Kathmandu valley with the intention to dedicate their lives to the service of AIDS victims.

Sensing there was more to this story I asked Shyam to fill me in on how he came to be here. This is his story:

I Shyam (name changed) was happy young boy living with my parents, sisters, and brother in Patan. I was doing ok in my studies in school. A friend of mine was telling me about his experiences, happy, pleasant. He tried to show me that he was different; better and cool, a smart boy. I wanted to be just like my friend. One day I joined his crowd, puff made me! I was a cool boy. "Hey" guys I'm one of you but I'm a hero.

My first introduction with drug started with all kinds of drugs. As I involved with drugs, sources where to get them, how to get money from parents and sisters. I wish and pray nobody should enter in this hell. My parents tried everything to help me to get out from that death canal. I also tried to stop but I can't express the craving, very strong you want to give up every thing to get those drugs. I can be sober for a few hours then I did everything.  "I don't want to remember those days now.  My sister used to tell me "Bara Baje pacchi boxi aauncha." Brother becomes a witch after 12pm.  I even tried methadone treatment, but nothing can substitute my drugs."  I lost so many friends,

It was over 10 years back that I became sick and later discovered I had caught HIV. Seeing other HIV victims at the clinic really opened my eyes and I found new friends. People just like me and from my town too. There were lots of them.

I came into contact with the leader of NKP in Kathmandu while being treated with ARV therapy. This was my opportunity. I learned about so many innocent people getting HIV from no fault of their own. It really broke my heart.

I came here and now many of my friends have come too. I love and care for PLHA from my heart, nothing can change my mind to feel their feelings, suffering and pain. One cannot express how they are living in very discriminatory complex communities and even their families discriminate against them.

3.5 Financial Evaluation of the RAB Project

3.5.1 Background:

Social Welfare Council (SWC) and Family Health International (FHI – Nepal) signed the general agreement on June 10, 2004. Further, a specific Project Agreement was signed between SWC and FHI – Nepal on February 01, 2006 with validity up to December 31, 2008 for undertaking programs related to HIV prevention, care and treatment for Nepali migrants at source and destination communities in Nepal and India.

The objective of the project is to focus on migrant communities in Far Western Nepal through mobilization of local Non Governmental organizations and supporting local Government health officials to establish HIV treatment and care services in two Government run hospitals.

On request of FHI Nepal, SWC has endorsed the extension of project tenure till March 31, 2009 without any change in total budget size but with some changes in budget line items.

3.5.2 Budget Estimate and Source of Financing:

As per the initial project agreement the budget estimate for the entire project tenure was as follows:

| Particulars | Yr. 1 | Yr. 2 | Yr. 3 | Total | Percentage |
| --- | --- | --- | --- | --- | --- |
| Administrative/ overhead cost | 62,225 | 75,604 | 101,339 | 239,168 | 14.85 |
| Program cost | 197,121 | 570,367 | 604,419 | 1,371,907 | 85.15 |
| Total Amount (USD) | 259,346 | 645,971 | 705,758 | 1,611,075 | 100.00 |

The entire funding is to be provided by Department for international Development (DFID), Head Quarter (1 Palace Street London SW1E 5HE) as financial grant.

3.5.3 Scope of work for Financial Evaluation:

The scope of work included the following aspects and general work procedures:

- Reviewing compliance with the general agreement and the project agreement

- Assessing efficiency and cost effectiveness of the project

- Reviewing accounting, administrative and internal control mechanism of the project

- Reviewing compliance with the Tax laws of the country

3.5.4 Financial Evaluation Methodology:

This evaluation report is based on:

- Review of terms reference of agreement documents, periodic reporting documents like audited report, management reports provided by the project – RAB and the local NGO partners of the project.

- Direct interaction with the office bearers of the project and the associated local partners and actual beneficiary of the project during the 7 days field visit.

- Sample testing of financial transactions wherever available. This includes local partner NGOs like Community Development Forum, Doti, Nepal Red Cross Society- Kailali, Nepal STD and AIDS Research Centre (only field office), Nava Kiran Plus (only field office). Local NGO partner – Social Awareness Centre not covered evaluation visit.

General observation and comments:

3.5.5 Financial Rules and Regulations:

In case of the financial transactions of the RAB Project, it is found to be governed by the set of rules and regulation of the Family Health - Nepal which in turn is governed by the global financial operational policies, rules and regulation of Family Health International. All other financial transactions related to the project works implemented by the local NGO partner of the project are found to be governed by the terms and conditions set forth in the respective sub-agreement between the FHI- Nepal and the respective local NGO partners.

3.5.6 Comparison of Budget and Actual Expenditure:

The comparative chart of total original budget, total revised budget and actual expenditure status of the project is presented below:

| Particulars | Original Budget | Revised Budget | Expenses as of February end 2009 (Provisional)* |
| --- | --- | --- | --- |
| Administrative Cost |  |  |  |
| Salaries | 102,750 | 105,802 | 68,392 |
| Procurement | 53,939 | 27,146 | 27,146 |
| Overhead | 82,479 | 94,038 | 111,516 |
| Total Administrative cost | 239,168 | 226,985 | 207,054 |
| Program cost |  |  |  |
| Program Staff salaries | 101,211 | 108,279 | 92,349 |
| Consultants | 112,811 | 137,888 | 61,605 |
| Travel | 73,636 | 60,411 | 54,364 |
| Procurement (Drugs) | 387,827 | 222,204 | 158,313 |
| Field Training, Workshop and other expenses | 98,005 | 154,457 | 79,037 |
| Sub-agreement | 598,418 | 700,852 | 687,274 |
| Total Program Cost | 1,371,907 | 1,384,089 | 1,132,941 |
| Total Cost (administrative + Program) | 1,611,075 | 1,611,075 | 1,339,995 |
| Admin% over Total cost | 14.85 | 14.09 | 15.45 |
| Program% over total cost | 85.15 | 85.91 | 84.55 |

* Note : Above cumulative figure is provisional including audited figures for period from February 01, 2006 to March 31, 2008 only.

Grant Utilization Ratio for Admin Cost and Program Cost:

Above tabulated figures reflects that the grant utilization ratio on Admin Cost and Program Cost as of February end is around 15.45% and 84.55% respectively. This shows marginal deviation above the standard level of administration cost. But as explained by Finance Officials of the project this will be well within limit after taking into account all other pending expenses pertaining to last month of Project tenure i.e. March 2009.

As explained by the Finance Officials of FHI- Nepal, the RAB project has adopted a system of calculating and charging administrative cost like salaries of administrative staff working at FHI Nepal looking after RAB Project on part time basis and overhead cost into the respective projects based on the 'Modified Direct Cost method' prescribed by FHI, Head Office.

3.5.7 Procurement of goods and services:

As explained, FHI Nepal has a practice of short listing vendors for procurement of stationary items on annual basis.

Standards procedures for procurement of goods and services like:

- Direct purchase of consumable items worth up to NRs, 3000/- directly from market

- Purchase against Procurement request for purchase up to USD 500/-

- Seeking 1 quotation for purchase worth above USD 500 to USD 2,499/-

- Seeking 2 quotation for purchase worth above USD 2,500 to USD 5000/-

- Seeking 3 quotation for purchase worth above USD 5,000/-

- Approval of FHI –HO for procurement of Drugs mandatory

are followed as prescribed in the procurement guidelines of FHI, HO and FHI Nepal.

However, Procurement of goods and services related to items under sub-agreement between FHI Nepal and local Ngo partners are executed as per the sub-agreement and under approval of FHI Nepal. The local NGO partners get reimbursement of the funds involved after procurement and approval of FHI Nepal.

Although Financial Rules and Procurement Policy document are not provided for review, on the basis of explanation provided, it is observed that in general, standard procedure for economic procurement process is found in place.

3.5.8 Compliance with General Agreement/ Project Agreements:

Source of funding and Disbursement modality:

As per the Project Agreement, the funding of the project operation cost is borne by DFID as financial grant and mode of disbarment is periodic (monthly) release of funds into the Bank account of the FHI (Nepal by DFID through FHI, HO - Arlington . FHI Nepal gets funding in USD accounts and transfer to NRS account as and when required as per the need. For the accounting purpose the USD to NRS conversion is calculated on the weighted average foreign exchange rate for the respective period of reporting.

Actual Financial Support Vs Committed Support:

FHI maintains USD and NRS savings account with Standard Chartered Bank for routing all financial transaction. However, it is observed that it does not maintain separate account for RAB Project. All financial transactions related FHI Nepal, other USAID projected implemented By FHI along with the RAB project is routed through the same accounts. Because of large of number of transaction, it is a tedious job to ascertain/ verify the receipt of funds for the RAB projects.

However, as per the audited report of the RAB Project for the period the receipt for grant funds from DFID are as follows:

Period from February 01, 2006 to March 31, 2007 	NRS 15,424,915.17

Period from April 01, 2007 to March 31, 2008	NRS 24,126,521.64

Further,

As per provisional report receipt of grants funds during period April 01, 2008 to February 2009 amounts to NRS 94,506,480

Thus, total grant receipt by the project as of February end 2009 amounts to NRS 94,506,480 which equivalent to USD 1,339,995 only. This total grant amount is 83.17% of the committed grant amount of USD 1,611,075/-. After the closure of account of the project on March 31, 2009 i.e. after taking account of payment of all pending expense items, this total grant amount is expected to be around the committed grant amount.

Actual level of activity vs committed level of activity:

As per the Project Agreement, the activity-wise breakdown of budget is provided in the annexure which is summarized below:

| Output | Description | Activity | Budget (USD) |
| --- | --- | --- | --- |
| 1 | Expansion of the safer migration initiative HIV prevention activities to Doti district in Far West Nepal | Various activities | 354,338 |
| 2 | Establishment of a care and treatment service for HIV positive Nepali migrants and their families in Mahendranagar and Dhangadi in far West Nepal | Various activities | 812,165 |
| 3 | Continuation and strengthening of existing HIV prevention activities for Nepal male migrants and their families in Mumbai and Thane | Various activities | 53,586 |
| 4 | Programmatic expansion of services in Mumbai and Thane to include limited scale care and treatment services for Nepali migrants and their families | Various activities | 99,842 |
| 5 | Extension of prevention activities to Surkhet and establishment of a care and treatment service for HIV positive Nepali migrants and their families in Kailali. | Various activities | 291,144 |
| Total: |  |  | 1,611,075 |

The activities outlined in the output # 3 and 4 totalling funds value USD 153,428 have not been undertaken by the RAB project. The project extension request and SWC endorsement also does not include any kind of changes in project activities, it only mentions about some changes in item budget lines. Thus, while evaluating the project on the basis of activity-wise budget breakdown, there is a lacking observation in updating/ seeking approval for changes in proposed activities of the project.

Expenditure in Non Budgeted Areas:

The estimated budget line provided in the Project Agreement is extremely broad in nature. Thus, in the context of the estimated budget line provided in the project agreement, no expenses are noticed during evaluation to be contrary to the budgeted line items. For the purpose of better monitoring and control, it is suggested that there should be detailed breakdown of budget line on annual basis.

3.5.9 Compliance with Tax Laws:

Neither the RAB Project nor FHI - Nepal has been registered with Tax Office. Thus, RAB project and FHI – Nepal has not got the 'Tax Exemption Certificate' because of which it has to forgo benefits like exemption of tax on its interest income on outstanding bank balance held in the savings account. It is suggested to register and obtain PAN and tax exemption certificate and adhere to requirement of periodic tax return filing.

RAB Project has been adhering to tax laws related to income of all staff entitled regular salary/ remuneration.

RAB Project has been adhering to tax laws related to Tax deduction at source (TDS) pertaining to payments related to procurement of goods and services. Similarly, tax law's provisions related to TDS deduction pertaining to payment of consultant services is adhered to.

Sample checking has reflected that deposit of such tax amounts deposited to concerned Tax office within the stipulated time frame.

During the field visit, compliance with the tax laws were examined for local NGO partners on sample checking basis and the following were the observations:

- Community Development Forum, Doti district has not been registered with the Tax office.

- Community development forum, Doti has not accounted "Allowance and Festival Allowance" Tax calculation on salary of the staff. This may result into additional burden to the organization if Tax office asks for the same.

3.5.10 Record of Fixed Assets:

The cost of fixed assets acquired by the RAB Project, FHI – Nepal and its local NGO partners are written off ( marked as expense) on the date of purchase. For control and monitoring purpose a memorandum of record pertaining to list of fixed assets along with status and probable life tenure is maintained. There is no system of calculating depreciation on the fixed assets. It is recommended to adopt accounting system of calculating and charging depreciation on the fixed assets of the project for true value of fixed assets of the project at any point of time.

RAB Project implemented by FHI Nepal has maintained up to date fixed assets register in the electronic forms. The list of fixed assets are segregated into two groups for value up to USD 1,000/- and above USD 1,000/-.

As substantiated by the periodic reports, FHI Nepal has practice of periodic physical verification of fixed assets under its control as well as fixed assets provided to the local NGO partners under sub-agreements.

During the field visit, sample checking of inventory list was conducted in the RAB Project Office located at Dhangadi as well as local NGO partner's office and medical treatment centres like ART Clinics/ Hospitals and it was found in order with proper coding and numbering.

As per the terms and condition of Project Agreement and sub-agreement between FHI – Nepal and local NGO partners, fixed assets provided by the RAB project to the respective local NGO partners needs to be returned to FHI Nepal on completion of the project term, unless FHI Nepal approve to extend the assets on permanent basis. Although the tenure of sub-agreement of all the local NGO partners expired on February end 2009 and the respective local NGO partners have requested for the same but final decision is yet to be provided. It is suggested to obtain clear decision on the issue at the earliest and act accordingly.

Regarding fixed assets, mainly machinery and equipments extended to Mahakali Zonal Hospital and Seti Zonal Hospital by the RAB Project, there is a proper practice of documenting handover and receipt recording system. However, we have observed list of such donated equipment in the inventory list of the RAB Project. This will be double counting of fixed assets and needs to be corrected at the time of handover (permanent delivery unlike in case of local NGO partners) itself.

There is no provision related to disposal of fixed assets during the tenure of the project. It is suggested develop and adopt suitable policy in this regard for the best economic interest of the organization.

During field visit, the Team observed that about 40 units of furniture like Hospital Bed -Side Table were stored at the project office at Dhangadi. On inquiry, it was explained that they are to be delivered to Zonal Hospital. This has reflected that the Project is in process of utilization remaining budget at the end of project tenure i.e. last week of project tenure. This behaviour does not sound prudent practice.

3.5.11 Financial System/ Reporting & Internal Control System:

RAB Project, FHI Nepal uses accounting system prescribed by the Family Health International and all financial transaction are carried out in line with the financial rules and regulation of FHI – HO and financial rules of FHI Nepal and the financial authority are entrusted inline with the same policy document.

RAB Project, FHI – Nepal does not have separate internal control unit to handle internal control system. It has not formulated any guideline for internal audit, scope, role responsibility and frequency of internal audit functions.

However it has adopted system of clear segregation of job line for double checking to mitigate incidence of overlooking and controlling manipulation at all stages. For example; administrative process of any procurement is handled by Administration Unit but checking execution of financial transaction like payment is handled by Finance/ C & G Unit. However, both of these Units reports to the same higher officer – Associate Director – Finance and Administration.

Similarly, all financial transactions are handled by FHI Nepal Head office and the RAB Project Office just act as facilitator to project implementation agencies.

All grant are received in USD currency and deposited in the account of FHI from where it is transferred to NRS account as and when required. Reporting to FHI Head office is done in USD whereas local financial transactions are done in local currency NRS. Currency conversion is done on the basis of weighted average foreign exchange rate over the period of transaction.

As the same account is used for different projects run by FHI Nepal, separate reporting related to RAB project is done on the basis of specific financial transaction code assigned to the project works. RAB Project, FHI - Nepal follows cash basis of accounting for recording the income and expenditure of the project. There is no system of depreciation charging.

Funds disbursements to Local NGO Partners are handled on reimbursement basis in the interval of monthly basis. Local NGO Partner are required to claim the reimbursement on monthly basis with supporting documents in line with the sub-agreement appropriate expenses are approved and accordingly funds are disbursed to their respective bank account by FHI- Nepal.

Consumables Inventories like office stationary are charged off in the accounts as and when purchase.

External Audit: The Income and Expenditure Account of the Project is audited by Chartered Accountancy Firm for each fiscal year adopted by the FHI – Nepal. The books of account of the local NGO Partners are audited by their own external auditors. However, as per the sub-agreement between FHI and local NGO Partners, FHI - Nepal reserves the right to audit the books of account of local partner whenever required.

RAB Project, FHI – Nepal has adopted periodic (monthly) reporting system for financial transaction with system of bi-monthly review on top of the annual financial reporting, statutory auditing, submission and disclosures in reports ensuring uniformity and overall review of financial good governance. Financial statements comprising of Income and expenditure statements presents a true and fair view of RAB Project, FHI – Nepal.

3.5.12 Comparison of Budget and Actual with Committed Project Cost:

Budget preparation process at FHI – Nepal depends on the project size and the requirement of the funding sources. Preliminary works are conducted by the project Office and FHI – Nepal Head Office will co-ordinate with FHI Regional Office and FHI Head office and funding Agency for finalizing he level of details breakdown of the estimated budge and finalize the same on year to year basis and for he entire project tenure.

The comparative details of budget (revised) and actual project cost of the RAB project on year to year basis is presented below:

| Particulars | Budget (Feb 1, 2006 – Jan 31, 2007) | Expense (Feb 1, 2006 – Jan 31, 2007) | Budget (Feb 1, 2007 – Jan 31, 2008) | Expense (Feb 1, 2007 – Jan 31, 2008) | Budget (Feb 1, 2008 – March 31, 2009) | Provisional Expense (Feb 1, 2006 – Feb end, 2009) |
| --- | --- | --- | --- | --- | --- | --- |
| Administrative Cost |  |  |  |  |  |  |
| Salaries | 23,134 | 11,148 | 23,610 | 17,709 | 76,945 | 39,535 |
| Procurement | 26,950 | 21,207 | 10,550 | 5,721 | 218 | 218 |
| Overhead | 65,252 | 33,706 | 62,327 | 32,892 | 27,440 | 44,918 |
| Total Administrative cost | 115,336 | 66,061 | 96,487 | 56,322 | 104,603 | 84,671 |
| Program cost |  |  |  |  |  |  |
| Program Staff salaries | 31,238 | 15,054 | 31,880 | 23,912 | 69,313 | 53,383 |
| Consultants | 4,449 | 776 | 10,429 | 618 | 136,493 | 60,211 |
| Travel | 17,493 | 16,915 | 21,502 | 15,695 | 27,801 | 21,754 |
| Procurement (Drugs) | 80,225 | 75,791 | 141,854 | 44,446 | 101,967 | 38,076 |
| Field Training, Workshop and other expenses | 63,536 | 10,559 | 106,159 | 12,775 | 131,123 | 55,703 |
| Sub-agreement | 176,471 | 70,319 | 296,662 | 243,874 | 386,659 | 373,081 |
| Total Program Cost | 373,412 | 189,415 | 608,486 | 341,319 | 853,356 | 602,207 |
| Total Cost (administrative + Program) | 488,748 | 255,476 | 704,973 | 397,641 | 957,960 | 686,878 |
| Admin% over Total cost | 23.59 | 25.85 | 13.68 | 14.16 | 10.91 | 12.32 |
| Program% over total cost | 76.41 | 74.15 | 86.32 | 85.84 | 89.09 | 87.68 |

(Source: RAB Project, FHI Nepal Finance Office)

Note: Above table of year-wise comparative funds utilization reflects that the ratio of Admin cost to the total project cost is higher than the standard level of 15% in the first year of operation.

However, this is worth noting that the above comparison is based on the revised annual budget of the project rather the initially approved annual budget as prescribed in the Project Agreement So the total sum of annual budget of three years exceeds the total Project Cost of USD 1,611,075/-..

3.5.13 Recommendations:

- It is recommended to have separate Bank account for each project managed/ handled by FHI – Nepal so that account reconciliation could be done easily and financial transaction pertaining to particular project could be traced easily. This will be helpful for verification of receipt of grant on the account and also facilitate income recognition of interest income earned in the Bank account.

- It is recommended to have a separate unit for monitoring internal audit aspect of financial transaction rather than depending upon dual checking system to have clearly define job-line and mitigate chance of any manipulation.

- It is recommended that the financial support provided to local NGO partners to cover administrative cost and organizational strengthening of such NGO be accounted separately and considered as Administrative cost. Similarly, it is recommend starting accounting practice for taking into account the depreciation of fixed assets depending upon the nature and life tenure of the fixed assets.

- It is recommended to register all such projects with concerned TAX office and obtain PAN along with Tax exemption certificates so that other income of the project like interest income could be free of any tax liabilities.

- It is recommended that the Monitoring Team of the Project shall also monitor the local NGO partner for their adherence to laws of the country like Tax registration, Tax collection/ deposit and timely return filing etc.

- It is recommended to update the fixed assets records pertaining to machinery equipments already handed over to other entities on permanent basis. It is also recommended to decide the issue of allowing local NGOs to use fixed assets provided by RAB Project on a permanent basis.

SECTION IV
SUMMARY, CONCLUSIONS and RECOMMENDATIONS

  - Summary - Analysis of Findings

4.1.1 Migration, Demography, Risk Behaviour, and HIV Prevalence

This evaluation confirms the underlying project assumption that Far Western areas of Nepal are in the grip of rising HIV that presently shows no signs of coming down. It also confirms the view that migrant workers returning from periods in India have, at least until recently, been a principal vector for transmitting this disease causing virus into their home communities.

Discussion with PLHA groups, NGO workers, and medical specialists together with detailed interviews has confirmed that large numbers of working age married and unmarried men travel to India for employment and that this migration involves nearly all the male working age population. NGO management interviewees were able to clearly identify demographic factors concerning the migrants and the source communities from which they typically originate.

They confirmed that migrant workers are mostly married and unmarried men, mostly of lower castes (particularly Dalit) owing to poverty but including a significant proportion of Chhetri caste. The common originating localities given include: Aacham, Baitadi, Bajang, Doti, East Doti, Daldeldhura, and Kanchanpur. It was also stated that most of the men remain in India for about 4- 5 years. It was also confirmed that Nepalese migrants are concentrated in highly specific locations in India; commonly including Delhi, Bombay and Pune in Maharastra, Punjab, and Gujarat.

NGO workers also advised that confidential interviews with migrant workers confirmed that commercial sex is a common factor in the experience of a high proportion of these men while residing in India and is considered the principal source of infections. The discussions revealed that it is usual for male migrants to have their work positions terminated once their Indian employer discovers that they are HIV positive. By the time HIV infected migrants return home, they are usually sick.

This aspect of the field research confirmed the underlying project assumptions about migration, risk behaviour and migrants as a vector for HIV transmission. What stands out is the extremely large number of individuals involved in labour migration. It was stated that in certain communities practically every working age male participates in this migration at some point in their lives, usually while in their 20’s and 30’s.

The enormous extent of labour migration and the risks involved raised questions about the actual prevalence of HIV in the population. It was surprising to the evaluation team that in the course of its efforts in HIV prevention and treatment, the RAB project did not appear to have produced coherent research based information on HIV prevalence and demographic models that might assist in more precisely targeting future prevention efforts.

Despite this apparent lack of research data, the RAB project’s vital statistics hint at a possible HIV prevalence indicator. Taking a simple arrangement of the number of HIV positive cases identified (in round figures; 600) from the total number of VCT tests performed (in round figures; 8,000) suggests that HIV prevalence among Nepali migrant workers returning from India might be in the region of 7.5%. This is obviously a very crude measure and without knowledge of biases in the pre-screening and selection of VCT subjects it was difficult to know whether the input figures were representative and if the result is in fact meaningful.

The written reply to executive questions put to the project owner and designers concerning this point denied the validity of using this result as it was considered that VCT subjects were self selected as being ‘at risk’ of HIV infection and its use might therefore lead to an overestimate of HIV prevalence among workers migrating to and from India. Instead they preferred to rely on a 2008 Integrated Behaviour and Biological Survey (IBBS) conducted in the project area that claims to show a general 1% HIV prevalence among male migrants to India rising to 5% among those who worked in Mumbai and who also admitted to sexual contact with female sex workers.

Nevertheless, these survey based estimates are challenged by a paper presented by Gurubacharya DL and Gurubacharya VL to the 15th International Conference on AIDS 11-16 July,2004, Bangkok, Thailand. In this paper attributed to the Kathmandu Medical College and Hospital, Kathmandu, Nepal, the researchers state their findings that; while HIV prevalence among Nepali migrants within Nepal is 2.3%, it rises to 8.9% among migrants working in India. They go on to state their conclusion that “Nepalese migrant workers are in special risk for acquiring HIV infection because of unsafe sex practice in comparison to workers within Nepal.”

A further reference to current literature on HIV prevention published in the 2008 special issue of THRIVE magazine, president of AIDS Healthcare Foundation, Michael Weinstein asserts that we are now in the era of the ‘one minute test’. If such technology is available it could be used and deployed on a massive scale.

The review was also concerned to gain a clearer understanding of the size and extent of the project’s intended target group. While the intended beneficiaries are identified in the project documentation simply as: ‘Nepali male migrants and their families’ this review has assumed that the intended beneficiaries are limited to male migrant workers (and their immediate families) who travel between far western districts of Nepal and locations in India, and who might be considered to be at risk of contracting HIV  and thereby transmitting the disease causing virus to their home communities in Nepal.

No reference can be found in project documentation to estimates of the size of this population and hence it is difficult to gauge the degree to which project activities have reached the potential target group. Nevertheless some attempt can be made to determine an estimate. It is stated that the total migrant worker population is in the range 7-14 Lakh. If we take the average figure of 10.5 lakh and assume one third hail from the Far West, the annual migrant numbers that this project is concerned with might be in the region of 3.5 lakh. If we then factor this estimate (x3) to reflect immediate family members, the target numbers expand to a figure more like 10 Lakhs. This compares with the projects achievement of contacting 1 Lakh of persons. Here we find a possible contact ratio of 1:10 in the target group.

In the NGO management interviews, respondents were asked if there should be some control (official or otherwise) over migration involving testing. Most respondents stressed the importance of pre and post migration HIV testing and agreed that mass testing would be of immense value in stemming HIV transmission from India.

Issue: This evaluation was concerned about how such a serious epidemic can be managed without a determined attempt to identify the carriers. There is also concern about the state of knowledge as to the true HIV prevalence among Nepali migrants to India and whether a survey could possibly be a realistic substitute for actual testing?

Issue: Is quick result mass testing a possibility and would this help to determine the actual prevalence of the HIV virus in the population and relevant demographic factors that might be used in helping to control an epidemic?

4.1.2 HIV Awareness & Behaviour Change

The review confirms that through RAB, significant effort has been put into community based initiatives to create awareness and knowledge about HIV in the hope that it would lead to positive behaviour change especially among at-risk segments of the population. Interventions such as CDF’s ICC outreach programme have clearly been targeting messages and encouraging individuals to participate in VCT. Nevertheless, after several years the evidence made available to this evaluation for enhanced awareness, knowledge and behaviour change was decidedly mixed.

NGO interviewees were asked about how effectively the project reached these communities (supplying migrant labour). Respondents felt that while the ICC and VCT programmes were very good at disseminating information the overall consensus was that the impact (on behaviour change) was not high and that general awareness about HIV/AIDS was still only low to medium. More specifically they typically assessed the general level of knowledge in the community about HIV and how it can be transmitted as only “A Little” or “Some”. Comments from the medical staff and DDC representative at Doti District Hospital ART centre confirmed that while people were prepared to speak more openly it was difficult to detect signs of behaviour change.

Respondents were somewhat divided as to the level of local awareness about this project but the overall consensus was that it was not high. However they were unanimous in identifying direct presentation activities as the most effective means of creating awareness and knowledge on HIV/AIDS. They went on to nominated outreach activities such as HIV awareness in schools, story telling in common local dialects, and video shows as particularly effective. They also considered the CBHC programme had helped to create greater local awareness about the HIV/AIDS issue.

When asked to nominate activities that they considered might have been more effective in creating awareness and knowledge about HIV, respondents frequently mentioned video, radio and other media presentations in common local dialects rather than in standard Nepali. They also considered that more VCT services would be most effective for expanded screening activities.

Senior NGO members when asked if it was possible to measure the effectiveness of the awareness and education programme in reducing HIV transmission provided a range of answers from impossible to possible only with the aid of a regular survey. Another considered it might be possible but only with access to records from all VCT camps and from health posts and sub health posts. Mass testing was also considered likely to be a highly useful approach.

When a similar question about the capacity of the project to measure effectiveness in reducing HIV transmission was put to the project owner and programme designer, it was acknowledged that measuring prevention programme effectiveness would require analysis of HIV incidence rates and that they do not have studies to do that. Furthermore the project owner admitted that with multiple overlapping HIV prevention projects in the far west, it might not be possible to attribute any reduction in HIV incidence to a single source.

It is the finding of this review that the RAB project has for whatever reason not attempted or been able to develop any objective methods to measure or assess the effectiveness of its efforts in HIV prevention. It is claimed that through its outreach programmes the project has directly contacted over 100,000 people for imparting its HIV awareness message. Yet the question remains as to whether these outreach activities are connecting with the most at-risk or simply the easiest people to access. Soft activities such as the Radio Listener’s group programme strongly suggest the latter.

While senior NGO members considered it would be difficult to objectively measure effectiveness in reducing HIV transmission without access to a lot more information, they all considered that direct presentations such as video in local dialects and cultural idiom rather than standard Nepali would be most effective, in reaching target groups, for creating awareness and conveying authentic information about HIV/AIDS.

Respondents identified key areas of learning from the project included the need for education and media presentation materials to be based in the local common language and cultural idiom.

The evaluation is also concerned about the potential effects of traditional gender relationships in impeding effective communication between women to men on important and sensitive subjects such as human relations and HIV. It is considered unwise to assume that simply because a female was contacted and provided information that this will automatically get to her husband or that she will be able to influence his thinking.

It was observed and confirmed in NGO interviews that the majority of people contacted through the RAB project for HIV awareness messages were female. As was demonstrated with the radio listener’s group programme, unmodified traditional gender relationships can and often do create barriers to effective female to male communication. As was stated by women in these groups; ‘our men do not listen to us’.

This observation was underlined by a casual comment overheard in the community by a team member. “Mukh hunda hundai nak le pani kina khane” this literally means “who wants to drink water through nose when there is a mouth” The context was male to male conversation concerning information conveyed by the wife, and the implication was that men prefer to receive their information directly and may not always give serious consideration to the utterances of mere women.

Issue: The RAB project’s prevention activities appear not to be self assessing or to incorporate tools for measuring effectiveness. Therefore; the issue is whether outreach activities are connecting with the most at-risk or simply the easiest people to access, whether the message is having a tangible effect and whether the numbers being contacted (approx 1 lakh) are a proportionate response to the scale of the epidemic?

A further issue relates to the possible desirability of coordinating all HIV prevention programmes in a single region rather than allowing multiple overlapping efforts

4.1.3 Radio Listener’s Groups

The evaluation team discovered through interview, observation, and group discussion that the radio listener’s group programme was effective in directly reaching at-risk populations with an HIV/AIDS message owing to having encountered a gender barrier which had not been overcome by any other measures such as gender sensitisation events. However the review also recognised that these community meetings had spontaneously developed into the nucleus for women’s self-help groups (SHG’s). This was confirmed by reports that a voluntary savings and credit scheme was getting underway which has long been recognised as a key component of SHG’s.

Issue: Has the RLG initiative got itself caught in a gender relations cultural ‘cul-de-sac’ and is there an opportunity to convert RLG’s into a sustainable Self Help Group (SHG) programme, under NGO facilitation, incorporating pre-prepared HIV education material?

4.1.4 Reaching Across Borders

In a group meeting with PLHA’s the evaluation team heard a positive story about identity card based referral from two PLHA’s recently returned from India. However it also heard contradictory information from two others who for some reason or another failed to access free medication and ART supervision while in India, in one case with disastrous results.

The meeting heard an instance of a male who is under ARV treatment. He obtained a stock of medicine from Dhangadi Hospital to cover three months as a special case and went back to India for work, Another case cited involved the wife of a PLHA was sending ART medicines to her husband in India. Through discussion it emerged that therapy continuity is often informally supported by letter and telephone from family members in Nepal.

Concerning the coordination of prevention activities across the border the team has been required to rely on the report of the mid-term review for its information. This report on prevention activities noted the use of material from Desh Pardesh in local radio listener’s groups and also the use of familiar outreach techniques such as street theatre and promotion of condom day and world AIDS day events together with enhanced access to VCT services. Despite all these efforts the mid term evaluation report was far from encouraging and indicated that the prevention effort was ineffective in reaching the most ‘at risk’ members of the Nepali migrant worker population.

Furthermore the evaluation team learned that RAB project outputs 3 & 4, namely:

- Continuation and strengthening of existing HIV prevention activities for Nepal male migrants and their families in Mumbai and Thane

- Programmatic expansion of services in Mumbai and Thane to include limited scale care and treatment services for Nepali migrants and their families

were not undertaken, a variation in the project for which no explanation was given.

Issue: The question arises Is this project ‘Reaching across Borders’ in name only?  Because it is hard to find any convincing evidence to show coordination of cross border activities and programmes other than referrals?

4.1.5 Clinical Workload, Hospital Health Priorities and Sustainability

From interview responses and direct observation it was apparent that the MOH have provided negligible additional staff support for the additional workload entailed in ARV therapy. The evaluation team could not help noticing a large discrepancy between the cursory level of attention and poor quality of services available for PLHA’s at the Seti Zonal hospital’s in-house ward compared to the nearby FHI run OPD clinic. At the hospital’s in-house PLHA ward it was apparently necessary for members of the local NGO, NKP to provide stop gap patient support to cover for the very limited staff that was available. A similar situation was observed at Doti district hospital ART centre where staff members were heavily loaded and had little time to attend to PLHA cases.

Most clinical interviewees reported that the project had a medium to high impact on their workload in both laboratory and clinical services where an assistant was often needed. Laboratory technicians also frequently expressed a need for basic and refresher training in testing and related procedures which appeared to be a reflection of the high staff turnover that also seems to affect the clinical areas. At Mahakali and Seti, clinicians and senior management all expressing grave concern about their capacity to sustain workload on termination of the project.

While there was evidence of considerable technical capacity having been built at the four clinical installations visited, the evaluation team and senior management all expressing grave concern about the capacity to sustain workload, supplies and OI related drugs on termination of the project  particularly at Seti and Mahakali.  Furthermore home based ART treatment services are considered to be at risk of collapse following withdrawal of project resources.

Issue: PLHA & ART workload appears to be overburdening a hospital health system that is either unwilling or unable to accord HIV cases a higher priority. Is this an opportunity to transfer core responsibility to the NGO voluntary sector under medical supervision?

Issue: Opportunity to expand role of NGO’s such as CDF, NKP, Red Cross etc. in supporting PLHA’s with more training, equipment and medical supervision thereby relieving hospital workload?

Issue: PLHA’s are receiving excellent care from the voluntary sector but the same people while well trained in leadership and organisation skills are lacking in relevant health related technical skills

Issue: How sustainable are the treatment initiatives without open-ended funding, especially home care?

4.1.6 O.I. Therapy

While all patient respondents reported ‘No Charge’ for ART drugs it was a universal observation that the same was not true for O.I. therapies where none or only some of the prescribed medicines were provided free of charge. This situation is reflected in a frequently expressed clinical concern that while patients were fairly regular with ARV therapy they were not always so regular with medicines prescribed for O.I. conditions.

Issue: Reported non-availability of many O.I. drugs or their not being available free of charge

4.1.7 Patients’ Perspectives

The review team was very pleased with the quantity and quality of feed back from PLHA patients interviewed at clinics, at their homes and in a group meeting at Baliya.

All patients interviewed appeared to be fully aware of their health condition and familiar with the various medications and the importance of adherence and observing particular timing. Respondents reported being on ART for between 6 months and 3 years and most recognised that therapy would be needed for the remainder of their life span. Most respondents indicated that they were referred by NGO outreach staff. Some however identified their family members as the referring agent.

Most respondents understood how HIV is transmitted and how further transmission can be prevented. However they reported being stigmatised and that discrimination exists concerning enrolment of HIV+ children in schools and use of communal bathing facilities and water resources.

The review team discovered that despite claims that CD4 testing is done on a 6 monthly cycle, some 10 out of 40 PLHA’s present in a group meeting indicated that they had not had a CD4 test in the preceding 8-10 months.

About half of the respondents reported receiving healthy living advice but few considered they had sufficient means for more than a very limited diet. These responses were reflected in the observations of the evaluation team who noticed that almost all of PLHA’s appeared needy and were malnourished, under weight and/or anaemic especially affected children. All respondents indicated that they desired some form of Government support for food security, education of children, and for other medical conditions.

This concern about poverty was confirmed through the patient interviews where half of the patient respondents depended on selling their labour for their livelihood and only a few had land, animals, or some other source of income. It was however observed that the PLHA support programme and CHBC in particular has provided a way for PLHA’s to gain useful employment, to become relevant to the society and gain recognition.

Issue: The overwhelming issue arising from patient interviews appeared to be the effects of poverty particularly malnutrition and the clear need for poverty alleviation programmes and special nutritional support for many patients.

4.1.8 Poverty Root Cause and need for Comprehensive Development

NGO management interview respondents indicated that poverty alleviation should be accorded a high priority since it is the main underlying cause of most social ills. They also nominated income generation programmes and activities as a most effective way to reach the at-risk population.

In the Red Cross executive group meeting an NRCS board director requested the SWC representative, on the evaluation team; to urge Social Welfare Council to develop a policy to encourage INGO’s to engage in comprehensive development programmes aimed at alleviating poverty. It was suggested that individual INGO’s should not attempt to do everything and spread themselves too thinly, rather they should be encouraged to contribute their unique skills and strengths to a comprehensive development programme for particular areas or regions. He went on to explain that Poverty is the underlying issue which manifests in a multitude of social problems including HIV/AIDS.

Issue: Concerns expressed about multiple stand alone projects by INGO’s and need for more integrated multidisciplinary effort to promote community development and poverty alleviation

4.1.9 Analysis of Community Resource Mobilisation and Sustainability

The evaluation notes that, in Nepal, the RAB project is implemented through some eight separate organisations. Three of these are Government run hospitals and the remaining five are local community based Non-Government Organisations. On the Treatment and Care side of the project, where the imperative is to build up infrastructure and centres of technical competency, working with major Government hospital health sites is a sensible approach. Similarly, on the Prevention side of the project where the imperative is to quickly gain community ‘reach and traction’, it is clearly sensible to work through established NGO’s using well proven community based development techniques.

The review team members were heartened to see the extent to which the RAB project had utilised locally based NGO’s with the required experience in HIV prevention and care programmes. While the present programme has its roots in earlier interventions of a similar nature often using the same community based organisations, FHI must nevertheless be given much credit for helping to build up a considerable pool of local expertise and capacity.

The review however has noted a tendency to create stand-alone interventions where supporting more comprehensive community based approaches might have been more effective and sustainable. A key example of this was the radio listener’s group programme. While the review commends the use of content from Desh Pardesh, and supports the intent of the radio listener’s programme, it is concerned about the effectiveness and sustainability of an important channel for disseminating the project’s HIV awareness message in source communities for Indian migration.

The review team observed that the radio listener’s groups had in effect become women’s mutual support groups and that their continued existence depended on the provision of a community facilitator for organising the target community and funding for equipment and expenses. It was reported that some groups had extended their activities to include microcredit savings and loan activities and as such are clearly entering the social territory usually occupied by the well known ‘Women’s Self-Help Group’ (SHG) format.

Self-help groups frequently include income generation, microcredit, literacy, health and diet awareness, and training and education on a range of topics of interest to its members. The inclusion of the core income generation, microcredit and literacy programmes are usually sufficient to assure their longer term sustainability. STI, and HIV/AIDS awareness and support can easily be included as a part of an SHG programme. NGO’s such as CDF are considered well placed to initiate, establish and support this kind of social institution and associated capacity building. Accordingly, the review considers that continuation of this kind of intervention might be more usefully focussed on the creation of sustainable Self Help Groups, and that the HIV awareness and education materials be made freely available together with trained facilitators who could make periodic visit to affiliated SHG’s.

The review was also deeply concerned about the overall effectiveness of the RLG programme. The RAB project documentation appeared to place much emphasis on this initiative and it appears that the project had not only invested a great deal in the RLG programme but also relied heavily on it as a key channel for communicating authentic information about HIV and its prevention. What the evaluation team saw scarcely matched the rhetoric.  The confirmed non-participation by males means the RLG programme has failed to directly reach at least half of the most at risk population.

This was disappointing but not exactly surprising since it was difficult to understand what was originally expected of the radio listener’s group programme. To envisage that in traditional rural societies where gender barriers are deeply entrenched, that men and women would happily sit together ‘for a cosy fireside chat’ and listen to a discourse on a subject as sensitive as HIV/AIDS and human relations is simply not credible! It has long been standard practice in social interventions of this nature to run ‘gender sensitisation’ workshops separately for men and women well in advance of any combined sessions.

The programme design seems not to have taken this into consideration. The results suggest that a community based development approach might have yielded better results. It also adds to the weight of evidence attesting to the relative ineffectiveness of stand alone HIV prevention projects compared to those operating as part of a wider community development agenda focussed on alleviating poverty.

4.1.10 Project Structure Analysis

Analysing the original project definition is an area where the review team had the greatest initial difficulty. The RAB project ‘Logical Framework’ describes a hierarchy comprising a Goal, a Purpose, and a series of five Outputs and associated Activities. These headings all contain a mixture of goals, objectives, and programmatic themes that often lack clear achievement criteria.

Goal: The project evaluation team had little difficulty identifying the stated project Goal expressed as:

“Reduced HIV transmission and increased access to treatment and care amongst Nepali migrants in source communities in Far West Nepal and destination communities in India”

The review however considered this statement to be more of a summarisation of objectives than a true goal, a view confirmed by the presence of a set of four qualifying ‘Indicators’ for which no quantitative estimation could be found in any project documentation,. These were:

- HIV prevalence among Nepali migrant workers

- Proportion of Nepali male migrants who report buying sex in preceding 12 months

- Proportion of Nepali migrants who report condom use at last commercial sex

- Proportion of HIV-positive Nepali migrant workers accessing HIV treatment and care

This review considers that the Goal needs to capture the essence of the project it defines by incorporating a high vision. Without some overarching statement of an ideal outcome, or the situation the programme is striving towards, the project lacks a banner or standard that everyone involved can identify with.  Accordingly the review considered it might be helpful to propose a Goal statement containing the following elements:

“The RAB project envisages the creation of a situation where migration of Nepali workers to and from India is no longer a path for HIV transmission and where all HIV affected migrants are being treated and well cared for”

Objectives

In searching for a concise statement of project objectives, the review first considered the statement of Purpose provided in the logical framework:

“Increase condom use by male Nepali migrants and increase uptake of VCT, STI and HIV care and treatment amongst Nepali male and female migrants and their families in source and destination areas in Nepal and India”

This statement appears to have captured several elements of objective and is once again accompanied by the same four qualifying indicators listed above. Nevertheless this appears to be only part of the story, and fails to cover several of the programmatic themes such as outreach and education. It also lacks any clear target or achievement criteria.

As mentioned above, the logical framework proceeds to describe a further set of five ‘Outputs’ or programmatic themes. It was through analysis of these outputs and their supporting activities that the review was able to isolate the implied objectives from programmatic descriptive material. This analysis identified two major objective headings:

- Reduce HIV Transmission (Prevention)

- Expand Treatment Coverage (Treatment)

The analysis was then able to identify three sub-objectives or (programmes) under each heading making a total of six objective themes.

The product of this work can best be illustrated in the Project Structure Analysis table that follows on the next page.

Having isolated the implied objectives and sub objectives and placed them in logical order, the next task of the review was to consider the quality of the objectives and their capacity to guide project activity and, most importantly, to act as a control to help management ensure achievement of suitable targets.

Analysis showed that the sub-objective were mostly descriptions of existing programmes that were to be continued or in some cases extended to new areas. While reasonably specific and relevant, none of the objectives contained all the elements that would allow them to be subjected to rigorous scrutiny or allow achievements to be tested against some predetermined criteria.

Numerical Targets over Project Life

Through further analysis of the project activities and other project documentation including quarterly reports, a total of only six quantifiable targets were identified, namely:

  - Extension of community based peer education to 25 VDC’s in Doti

  - Establish 40 radio listener’s groups

  - 80,000 individuals contacted for prevention education

  - 380 (later 590) PLHA’s being treated through ARV therapy

  - 2,020 receiving treatment for STI’s and OI’s

  - 5,000 using clinical services

However, as can be seen, only the first two of these targets were explicitly connected to project activities and by implication to an objective.

Project Structure Analysis

|  | Project GOAL “The RAB project envisages the creation of a situation where migration of Nepali workers to and from India is no longer a route for HIV transmission and all HIV affected migrants are being treated and well cared for” |  |  |  |
| --- | --- | --- | --- | --- |
| Objective 1: Reduce HIV Transmission (Prevention) |  | Objective 2: Expand Treatment Coverage (Treatment) |  |  |
| “To reduce HIV transmission through enabling risk reducing behaviour change involving increased awareness and knowledge of HIV/STI causes, effects and prevention and increased uptake of voluntary counselling and testing for HIV/STI in far-west Nepal and in India” |  | “To expand HIV/AIDS treatment coverage through increasing access to treatment and care services among Nepali migrants in far-west Nepal and in destination locations in India” |  |  |
| Programme 1.1: Continuation and strengthening of existing HIV prevention programme for Nepali migrants and their families in Mumbai & Thane |  | Programme 2.1: Establish a care and treatment programme for HIV+ Nepali migrants and their families in Mahendranagar, Doti and Dhangadhi |  |  |
| Activity 1.1.1 Conduct needs assessment among Nepali migrant community |  | Activity 2.1.1 Collaborate with NCASC, MOH at Mahakali & Seti zonal hospitals and Doti district hospital to establish care and treatment services in Mahendranagar, Dhangarhi and Doti |  |  |
| Activity 1.1.2 Review BCI action plan, available BCI material and distribute at scale |  | Activity 2.1.2 Establish an outpatient service for PLHA that provides initial health check-up, cotrimoxazole prophylaxis, diagnosis and treatment of opportunistic infections |  |  |
| Activity 1.1.3 Conduct BCI communication services with a new group of people |  | Activity 2.1.3 Capacity building of hospital staff by (through) ongoing training and technical support in establishing a patient management information system at Mahakali and Seti zonal hospitals |  |  |
| Activity 1.1.4 Mobilise migrants’ for communities to mount community events aimed at reducing stigma and discrimination |  | Activity 2.1.4 Increase access, and strengthen the quality of the inpatient services provided for PLHA |  |  |
| Activity 1.1.5 Conduct innovative communication and community involvement activities using satellite broadcast radio programme developed in Nepal |  | Activity 2.1.5 Provide ART to eligible PLHA by establishing an ART committee |  |  |
|  |  | Activity 2.1.6 Strengthen cross-border continuity of care for HIV+ Nepali migrants |  |  |
| Activity 1.1.6 Identify and train peer educators for new geographic areas |  | Activity 2.1.7 Ensure HIV commodity security by procuring drugs and laboratory reagents and maintaining proper inventory management systems |  |  |
| Activity 1.1.7 Establish linkage with social marketing agencies for condom promotion and distribution |  | Activity 2.1.8 Provide patient follow-up and adherence monitoring through outpatient service |  |  |
|  |  | Activity 2.1.9 Reduce the risk of occupational exposure in Mahakali zonal hospital |  |  |

| Programme 1.2: Expansion of the ‘Safer Migration Initiative’ HIV Prevention programme to Doti district in Far-West Nepal | Programme 2.2: Expansion of programme services in Mumbai and Thane to include limited scale care and treatment services for Nepali migrants and their families |
| --- | --- |
| Activity 1.2.1 Strengthen the capacity of local NGO’s in conflict affected districts in far-western Nepal to implement HIV prevention programming | Activity 2.2.1 Provide care and treatment services including STI services and community based VCT |
| Activity 1.2.2 Extension of the Digital Broadcasting initiative in Doti by establishing 20 radio listener groups and train facilitators | Activity 2.2.2 Provide psycho-social support, home based care service, OI/ARV management and adherence support |
| Activity 1.2.3 Extension of community based peer education to 25 VDC’s in Doti |  |
| Activity 1.2.4 Promotion of & referral to STI, VCT, & HBC services in Doti | Activity 2.2.3 Train community volunteers and family members on home based care and support |
| Activity 1.2.5 Support PLHA support groups and PLHA network groups & PLHA networking in Doti | Activity 2.2.4 Provide health, nutrition, and social & educational support for migrants their wives and children |
| Activity 1.2.6 Coordinate above activities with other INGO’s working in same area; viz. Save the Children Norway, US CARE and relevant DDC’s |  |
| Programme 1.3: Extension of Prevention programme to Surkhet | Programme 2.3: Establish Care and Treatment Programme for HIV+ Nepali migrants and their families in Kailali |
| Activity 1.3.1 Extension of prevention and care activities in Surkhet | Activity 2.3.1 Establish STI/VCT services for migrants and their families |
| Activity 1.3.2 Establishment of STI/VCT for migrants and their families in Kailali | Activity 2.3.2 Establish HIV care and treatment services for PLHA in Kailali |

4.1.11 SMART Objectives

From inspection of the project structure analysis it can be seen that the implied objectives are noticeably deficient in objective measurement and targets, the qualities often referred to as ‘SMART’.  This is a set of criteria widely accepted as a standard in the Community Based Development discipline. These criteria are:

- Specific

- Measureable

- Achievable

- Relevant

- Time-bound

Issue: The review was most concerned about apparent deficiencies particularly in the second and fifth criteria for SMART objectives. The same lack of rigour and precision in target setting evident in the objectives seems also to extend to the associated activities where objective numerical success criteria and target achievement dates are seldom mentioned.

4.1.12 Control and NGO Participation

NGO management interview respondents indicated that one of their greatest concerns about the project was the need for much greater local involvement at every stage of the design process to ensure the programme meets its targets. This reflected the evaluation team’s observations that FHI has run this project in a highly centralised manner and also reflects signs and indications from the Dhangadi project office of staff frustration with the central office.

Issue: The observed degree of central control raises questions about how much delegated authority exists at regional office and how prepared the regional office is to engage in decision making and quickly adapt their approaches

4.1.13 Strategic Focus

Among the findings of the evaluation is a recognition that the RAB project attempts to pull together two very diverse programme strands into an integrated whole, namely HIV/AIDS Prevention and Treatment & Care. While the Treatment & Care strand clearly concentrates on medical and clinical disciplines with assistance from the mobilisation of community resources, the Prevention strand draws almost exclusively on social technology and community mobilisation.

Looking at the overall project from a management perspective the Treatment side of the project is focussed on building up well understood medical infrastructure in existing hospital health and other institutions and developing clinical and management capacities to handle large volumes in VCT testing and long term treatment regimes. The strategic intent in the treatment strand is to have the capacity and competencies to test and treat large numbers and effectively manage resources for a long term programme. Here the review found a clearly identifiable strategic focus with much attention given to implementing relevant technology and building up supporting technical capacities.

On the other hand the Prevention side of the project concerns itself with completely different considerations. It involves a less exact science and is focussed on finding effective responses to what can only be described as a ‘national public health emergency’. This can be compared to an army attempting to stop an invasion and it needs to be innovative, quick to adapt and change tactics, and highly resourceful. The strategic intent of the defenders is to halt the spread of HIV (as per the National Millennium target no.6) by all possible means and it seems only appropriate that such an important campaign needs strong leadership that is willing to be held accountable for success in this area alone.

This review was unable to find a clearly identifiable strategic focus and ‘burning attention’ to prevention. The written answer given by the project owner to the evaluation team’s fifth interview question appears to sum up the reality of the RAB project, Refer Section III page 27.  The fifth and final question quoted the old adage that “Prevention is better than Cure” and asked; what was the approximate proportion of RAB project resources that were committed to prevention versus treatment, the reason for the relative allocation and whether there should have been a greater emphasis on prevention. The following written response was given.

‘In this project 34% is spent on prevention activities and 66% on care, support and treatment.

Due to specific nature of the project, RAB had given priority on care, support and treatment component. Please note that USAID supported ASHA Project also implemented in the far west region and have also dedicated resources to HIV prevention activities’

This answer underlines this review’s finding that prevention activities have been accorded a secondary priority and lack strategic focus. The most curious part of this response was the reference to the parallel USAID supported ASHA project implying a justification for the lower focus on prevention, yet neither the existence of this project nor any arrangements, tacit or explicit, with ASHA were mentioned in the original proposal.

Issue: The RAB appears to comprise a medical oriented response to the HIV epidemic with a focus on treatment and care services not equally evident in prevention activities

4.1.14 Achievements

This review considers that the greatest achievements of the RAB project lie in the area of ongoing care and support arrangements for Persons Living with HIV/AIDS (PLHA’s). Since reliance on hospital health based support is clearly an unwelcome burden on Government health resources and, with growing numbers of HIV victims on antiretroviral drug therapy, also patently unsustainable, FHI’s support for Community Home Based Care (CHBC) is therefore viewed as both a positive and progressive move. The way ongoing support and care for PLHA’s has been arranged through organising the voluntary/NGO sector including groups such as Nava Kiran Plus, Community Development Forum, and Nepal Red Cross Kailali, is most encouraging.

One of the outstanding features of community based care is the creation of a number of care teams comprising professional NGO members working in partnership with rehabilitated PLHA’s. Members of the review team were at times overwhelmed by the immense depth of concern, compassion, and utter dedication exhibited among PLHA’s employed in these teams to care for fellow HIV victims. Not only is this seen as a highly effective approach, it is also seen as a powerful way to rehabilitate HIV victims, and create useful occupations leading to greater social recognition and status.

This review has witnessed the emergence of several strong leaders among PLHA’s and wishes to commend all those involved in these community based initiatives. We also wish to encourage the inheritors of RAB project to invest further in capacity building for the creation of genuine social enterprises engaged in the business of caring for, providing rehabilitation services, and for promoting economic development among the growing numbers of PLHA’s.

This review also wishes to acknowledge the achievement of RAB in creating technical centres of competence at significant Government hospital sites such as the outpatient ART centres at Doti and Seti. It was apparent to the members of the review team that faced with overstretched Government hospital budgets and bureaucratic structures; this achievement has been something of an uphill struggle and has involved a great deal of external funding to “prop-up” the hospital system. Whether these efforts and resources might have been better directed to the voluntary sector nevertheless remains a serious question mark.

FHI’s stewardship of the HIV treatment programme has also seen the establishment of universal free ART drugs for PLHA’s.

4.1.15 Effectiveness over time

The review found that the project was widely considered to have been slow to get started and begin to bear fruit. This slow getting started perception is also accompanied by concerns over the brief effective time period allowed for the project.

4.2	Conclusions

4.2.1 HIV Epidemic

While the RAB project has made impressive contributions in the related fields of treatment and care for PLHA’s the impact of prevention activities and their capacity to enable behaviour change and thereby stop the spread of HIV among the target population remains untested and of doubtful short term value. In fact it became strongly apparent to this review that soft sell awareness and education activities are at best a medium to longer term response to the HIV/AIDS problem.

While the size of the potential target group has not been estimated, this review considers it likely to be in the order of 10 Lakhs (1 Million) and, if this is true, no more than 10% have been contacted through project activities. Apart from the crude HIV prevalence figure of 7.5% taken from a simple analysis of the number of HIV cases detected out of the number of VCT tests performed, the evaluation has not seen any evidence that the RAB project has helped develop the kind of research based tools that might help gain a clearer understanding of HIV prevalence and advance the bigger battle to stop the spread of the virus and help Nepal meet its Millennium target of halting the spread of HIV by 2015.

Recommendation: This review wishes to recommend to the inheritors of RAB that well designed research strategies, most likely involving large scale HIV testing, be incorporated into the programme with the aim of finding out exactly how many people are infected and for developing models that may help target more effective interventions among all parties working in this field to halt the spread of HIV.

4.2.2 Awareness and Behaviour Change

This evaluation is unconvinced about the effectiveness of the present awareness programme which we found to be concentrated in ‘soft sell’, low profile activities lacking in strategic drive. Furthermore there was little evidence the HIV prevention message was getting to the most at risk populations.. The evaluation was also concerned about the absence of statistical and demographic profiling outputs from the prevention programme and reliance on Government statistics and results of surveys rather than the directly observable and verifiable results of its own activity.

Recommendation: This evaluation wishes to suggest to the inheritors of the RAB project that consideration be given to mounting a high profile campaign for mass testing in key target communities. This might involve hi-tech mobile large capacity testing centres supported by extensive publicity and various kinds of awards and incentives for participation. If carefully designed, one important output might be credible research models including demographic profiles, and reliable HIV prevalence statistics. Such a programme needs to take into account gender sensitivities.

4.2.3 Cross Border Reach

The evaluation team has formed the view that the title “Reaching across Borders” was more a term of initial intention and that while seeds for co-operation and coordination of services between Nepal and India have undoubtedly been sown; they are yet to fully sprout and bloom.

For some reason the project appeared to have abandoned activities associated with outputs 3 & 4 involving continuation and strengthening of prevention activities in Mumbai and Thane, and establishment of limited scale care a treatment services in the same areas, for which some $150,000 was budgeted. This project variation underlines the above view that cross border coordination has not been actively pursued on a broad front.

The project evaluation team received mixed evidence about the effectiveness of a card based referral system for Nepali PLHA’s where some gained service in India, just as many did not, and others still devised their own pragmatic approach by having relatives in Nepal send them their ART medicines every three months. Furthermore migrants appear to be scattered over a greater number of locations than has been recognised in the programme.

Concerning the coordination of prevention activities across the border, the RAB mid term report indicated that the prevention effort was ineffective in reaching the most ‘at risk’ members of the Nepali migrant worker population around Mumbai and Thane. From its own observations, the review team concluded that coordination with India has not been easy nor has it necessarily been given the highest priority.

Recommendation: The review wishes to recommend that the inheritors of the project to redouble efforts to create strong linkages to suitable existing PLHA support networks across all main centres in India rather than attempt to build their own services in a handful of localities. It is also recommended that future programmes concentrate prevention activities on the next generation of school leavers, who are likely to follow the well beaten migrant path established by their fathers, rather than on the older generation of migrant workers who may have developed entrenched attitudes and habits, who may not be open to accepting prevention messages and whose behaviour may not be readily amenable to change.

4.2.4 Poverty Alleviation and Comprehensive Development

The review is attracted to the argument presented by senior NGO figures that income generation and poverty alleviation programmes are best way to engage with and reach the hearts and minds of the most at-risk population. This argument holds that labour migration is a reflection of poverty in all its manifestations including; social marginalisation, discrimination, gender inequality and deprivation. In this context it is believed that HIV prevention programmes that are firmly embedded in comprehensive development initiatives are likely to be more relevant to the target group and therefore may be more effective over the longer run.

Recommendation: This review wishes to commend to the inheritors of the RAB project and to the Social Welfare Council of Nepal and NCASC, that ways be sought to mount innovative and comprehensive district or region wide development programmes. It is envisaged that these broad initiatives would utilise the specialised skills and resources of various agencies to pursue multidisciplinary development approaches in preference to the pursuit of individual overlapping and/or stand alone efforts.

4.2.5 Radio Listener’s Groups

While the evaluation was not particularly impressed with the effectiveness of radio listener’s groups as a means to reach the most at-risk population, it nevertheless commends their creation and is concerned that this effort towards building genuine grass roots community institutions not be lost.

Recommendation: The review wishes to recommend that ways be found to keep the infant women’s self help groups alive, if necessary by transferring the responsibility for their coordination to other community based organisations. The inheritors of the RAB programme can thereby gain access to ready made women’s groups without the direct responsibility for their facilitation and support.

4.2.6 Leveraging Community Resources for Sustainability

The evaluation has come to the inescapable conclusion that the Government hospital health system is overburdened and for whatever reasons unable to accord HIV/AIDS treatment and care a higher priority thereby allocating the necessary resources to provide what many would consider an adequate service to its victims. This evaluation has dealt at length with the treatment side of the RAB project and involved itself in great detail in many aspects of the programme’s medical responses to the HIV/AIDS epidemic.

Many of these responses are deeply enmeshed with support for the publicly organised health system, which despite this assistance has contributed negligible additional resources towards the expanded workload in ART and VCT services. By comparison the support given to community based responses to supporting victims of the HIV/AIDS crisis have been richly rewarded through dedicated and compassionate service at every level from attending to acute cases in understaffed hospital wards to maintaining home based care and community support networks for PLHA’s.

The evaluation nevertheless recognises that considerable technical capacity has been built at major clinical sites, yet we share the concern of their owners about the sustainability of VCT and ART services without the ongoing injection of donor funds to prop up the under resourced hospital system.

Recommendation: The review wishes to recommend that the inheritors of the RAB project use this transition in a positive way to begin the process of restructuring with the aim of putting service delivery to the growing PLHA community on a more sustainable basis. It is envisaged that this might be best achieved by transferring core responsibility for ongoing treatment and care services into the community through the various voluntary agencies that are already involved but under competent medical supervision. It is further recommended that capacity building resources be allocated to develop greater paramedical knowledge and skills among these same voluntary agencies that can become genuine Social Enterprises. This approach envisages a complementary role with the hospital system concentrating on providing services for acute care beyond the reasonable capacity of community based health service providers.

4.2.7 O.I. Therapy and Nutrition

The evaluation has reached the conclusion that while the RAB project has achieved a universal free ART drug system for PLHA’s, there are substantial gaps in the provision of essential drugs for complications (known as opportunistic infections) and for nutritional support which appears to be another near universal requirement. This is clearly a penny pinching response to a humanitarian crisis.

Recommendation: The review recommends to the inheritors of the RAB project, that future ART pharmaceutical budgets be reworked to include reasonable estimates for complementary OI therapies and essential nutritional supplementation.

4.2.8 Patient Centred Responses

The evaluation concludes that while RAB has made enormous strides to provide essential services to the growing PLHA community and in particular the positive role of the CHBC programme, however, owing to pervasive poverty, these unfortunate folk remain heavily dependent on various forms of welfare support. The review team was particularly impressed with arguments presented by the support NGO’s in favour of the potential for PLHA’s to improve their economic and social situation through appropriate development initiatives.

Recommendation: The evaluation wishes to urge the inheritors of the RAB project to give serious and urgent consideration to ensuring PLHA communities are included in any comprehensive regional development initiatives aimed at poverty alleviation.

4.2.9 Project Definition

The evaluation wishes to express its disappointment with the quality of the original project definition which is considered to suffer from a lack of clarity and precision in the area of goal and objectives to the extent that it has been difficult to determine both the original intentions and envisaged levels of attainment and to gauge its effectiveness and efficiency. The project definition does not meet the standards that could be reasonably expected of an undertaking of this magnitude and this weakness is also a impediment to adequate monitoring and evaluation.

Review of the original project definition revealed a frustrating degree of imprecision and lack of clarity concerning Goal and Objectives. As described in SECTION IV paragraph 4.1.10 above, the stated goal turned out to be a partial statement of the objectives and the same was true of an additional statement of Purpose, which when taken together still did not add up to a complete and clear understanding of the project objectives.

It was only through a detailed reading of a set of five project Outputs and their subordinate activities that the reader could gain some sense of the intended objectives.  Confusion continued however since these five outputs were in fact simply descriptions of programmatic themes that were to be either continued or in some cases extended from some earlier arrangements. Furthermore these outputs frequently cut across and combined disparate disciplines and were lacking in clear and measurable achievement criteria.

To help guide the evaluation it became necessary to attempt to set out what the review considered to be a best attempt at defining the goal and objectives. This is described in detail in SECTION IV Analysis of Goal and Objectives.

Recommendation: The evaluation wishes to recommend that if this project is to be renewed or any of the activities continued that the project definition should be thoroughly reworked using standard development profession terms and definitions, particularly SMART objectives, together with sufficient programme activity and associated budget detail to allow both effective management control and transparent monitoring and evaluation.

4.2.10 Partner Agency Participation

The evaluation has formed the view that much of the RAB project, particularly in the prevention programme, has been devised and implemented without strong participation from the partner agencies. In depth interviews with implementing agencies revealed deep seated concerns about the need for much greater local involvement at every stage of the design process as a means of helping to ensure a practical and effective programme that is capable of meeting its targets. The evaluation team’s observations on regional frustration with centralised management control raises concerns about regional participation and capacity building for local decision making.

Recommendation: The evaluation wishes to recommend that the inheritors of this project take advantage of the transition period to comprehensively re formulate the project using strongly participatory appraisal processes involving all partner agencies.

4.2.11 Project Structure and Definition

This evaluation is concerned that the RAB project contains structural issues and possibly inherited from earlier programmes in the same area. The review considers that in essence RAB as it has been operated consists in two very different kinds of response to the HIV/AIDS epidemic, one (Treatment) grounded in a predictable and clearly understood medical response, the other (Prevention) based in far more urgent, risky and difficult to manage community based responses with far less predictable results.

In considering the nature of the two major objectives, (Treatment and Prevention) the review questions whether these two components might be better managed through separate and distinct chains of command and participation. It reasons that where a tightly centralised management system may be appropriate for the medical response, the same may be far less useful and even dysfunctional for the fast moving community based prevention and defensive programmes.

When analysing the Prevention side of the project it became apparent to the review that RAB has been attempting to fight an epidemic use soft sell awareness and behaviour change activities. While awareness, education and behaviour change activities are undoubtedly vitally important in the own right, they need to be seen as a medium term response and not relied upon on their own to address the HIV crisis. The prevention component can therefore be further resolved into distinct aspect, each with their own corresponding objective:

- Prevention: Awareness, Education, and Behaviour change nested in medium term integrated development programmes aimed at poverty alleviation

Recommendation: The review wished to urge the inheritors of the RAB project to consider dividing the project into two separate but complementary programmes each under its own leadership, employing distinct and appropriate management approaches.

  - Treatment Care and Rehabilitation with an emphasis on community based responses

  - Prevention through Awareness Education and behaviour change built into ongoing community development and poverty eradication programmes

  - Recommendations

4.3.1 HIV Epidemic

Recommendation: This review wishes to recommend to the inheritors of RAB that well designed research strategies, possibly involving large scale HIV testing is incorporated into the programme with the aim of developing models that may help target more effective interventions among all parties working in this field to halt the spread of HIV. Other than this it would appear that limited interventions may only be working on the margins while waiting for the main thrust of the epidemic to burn itself out.

4.3.2 Awareness and Behaviour Change

Recommendation: This evaluation is unconvinced about the effectiveness of the present awareness programme and wishes to suggest to the inheritors of this project that consideration be given to mounting a high profile campaign for mass voluntary testing in key target communities. This might involve hi-tech mobile large capacity VCT centres supported by high publicity and various kinds of awards and incentives for participation. If carefully designed, one important output might be credible research models including demographic profiles, and reliable HIV prevalence statistics. Such a programme needs to take into account gender sensitivities.

4.3.3 Cross Border Reach

Recommendation: The review wishes to recommend that the inheritors of the project redouble efforts to create strong linkages to suitable existing PLHA support networks across all main centres in India rather than attempt to build their own services in one or two localities. It is also recommended that future programmes concentrate prevention activities on the next generation of school leavers, who are likely to follow the well beaten migrant path established by their fathers, rather than on the older generation of migrant workers who may have developed entrenched attitudes and habits, who may not be open to accepting prevention messages and whose behaviour may not be readily amenable to change.

4.3.4 Poverty Alleviation and Comprehensive Development

Recommendation: This review wishes to commend to the inheritors of the RAB project and to the Social Welfare Council of Nepal and NCASC, that ways be sought to mount innovative and comprehensive district or region wide development programmes. It is envisaged that these broad initiatives would utilise the specialised skills and resources of various agencies to pursue multidisciplinary development approaches in preference to the pursuit of individual overlapping and or stand alone efforts.

4.3.5 Radio Listener’s Groups

Recommendation: The review wishes to recommend that ways be found to keep the infant women’s self help groups alive, if necessary by transferring the responsibility for their coordination to other community based organisations. The inheritors of the RAB programme can thereby gain access to ready made women’s groups without the direct responsibility for their facilitation and support.

4.3.6 Leveraging Community Resources for Sustainability

Recommendation: The review wishes to recommend that the inheritors of the RAB project use this transition in a positive way to begin the process of restructuring with the aim of putting service delivery to the growing PLHA community on a more sustainable basis. It is envisaged that this might be best achieved by transferring core responsibility for ongoing treatment and care services into the community through the various voluntary agencies that are already involved but under competent medical supervision. It is further recommended that capacity building resources be allocated to develop greater paramedical knowledge and skills among these same voluntary agencies. This approach envisages a complementary the role of the hospital system concentrating on providing services for acute care beyond the reasonable capacity of community based health service providers.

4.3.7 O.I. Therapy and Nutrition

Recommendation: The review recommends to the inheritors of the RAB project that future ART pharmaceutical budgets be reworked to include reasonable estimates for complementary OI therapies and essential nutritional supplementation.

4.3.8 Patient Centred Responses

Recommendation: The evaluation wishes to urge inheritors of the RAB project to give serious and urgent consideration to ensuring PLHA communities are included in any comprehensive regional development initiatives aimed at poverty alleviation.

4.3.9 Project Definition

Recommendation: The evaluation wishes to recommend that if this project is to be renewed or any of the activities continued that the project definition should be thoroughly reworked employing standard development profession terms and definitions, particularly SMART objectives, together with sufficient programme activity and associated budget detail to allow both effective management control and transparent monitoring and evaluation.

4.3.10 Partner Agency Participation

Recommendation: The evaluation wishes to recommend that the inheritors of this project take advantage of the transition period to comprehensively re formulate the project using strongly participatory appraisal processes involving all partner agencies.

4.3.11 Project Structure

Recommendation: The review wished to urge the inheritors of the RAB project to consider dividing the project into two separate but complementary programmes each under its own leadership employing distinct and appropriate management approaches.

SECTION V - REFERENCES

- Gurubacharya DL and Gurubacharya VL research paper presented to the 15th International Conference on AIDS 11-16 July,2004, Bangkok, Thailand. Paper attributed to the Kathmandu Medical College and Hospital, Kathmandu, Nepal

- 2008 Special issue of THRIVE magazine, president of AIDS Healthcare Foundation, Michael Weinstein

- FHI – Quarterly reports on RAB numbers………………………………

- CBS – 2004 Nepal living standards survey, CBS Ramshahapath

- HDI – 2007, Human Development Report (2007/2008), UNDP

- NNSWA, 2006, “Safer Migration Initiative in the Far West Project VCT/STI Programme

- SWC/FHI 2006, “General Agreement Signed between SWC and FHI, Kathmandu Nepal

- SWC/FHI 2008 “Project Agreement signed between Social Welfare Council and Family Health International, Kathmandu, Nepal

- WOREC, 2002, Perceptions of Grassroots people about Human Trafficking, migration and HIV/AIDS Kathmandu, Nepal

- NCASC, 2007, National HIV/AIDS Strategy (2006-2011), Kathmandu, Nepal

- UNFPA, 2003, Evaluation Report #20, UNFPA’s Support for National Capacity Development Achievements and Challenges

- RECPHEC, 1995, Gender and Women’s Health: Challenges and Prospects, Kathmandu, Nepal

- UNAIDS, 2007, Nepal National AIDS Spending Assessment, Kathmandu, Nepal

SECTION VI - ANNEXTURES

6.1 Field Questionnaire

To assist in interviews with the staff of various implementing agencies, a set of guideline questions was prepared in advance and used as a questionnaire to be administered in the course of the review tour. The questionnaire was divided into six sections according to the function being evaluated. These are:

- Part A Managerial - Interview Questions for senior members of implementing agencies involved with either Social and/or Clinical services

- Part B Technical - Interview Questions for Clinicians and Laboratory Staff

- Part C Patient at Clinic – Interview Questions for Patients

- Part D Patient at Home – Interview Questions for Patients

- Part E Financial – Interview Questions for senior managers responsible for Accounting and/or Financial Controls in implementing agencies

- Part F Project Owner - Interview Questions for senior managers responsible for designing and promoting this Project

6.1.1 RAB Project Evaluation

Respondent Questionnaire

Respondent Number _____ Respondent Position Code _____Interviewer: _________________

| Part A Managerial - Interview Questions for senior members of implementing agencies involved with either Social and/or Clinical services |  |  |  |
| --- | --- | --- | --- |
| Row | Question | Confirmation | Responses |
| 1. | What do you believe was the goal for this project and the supporting objectives? | The goal is the dream and the objectives are the specific outcomes that help make the dream come true | Goal: Objectives: |
| 2. | Which of these objectives were you or your organization most involved with? |  | Describe: |
| 3. | What activities did you or your organization undertake to fulfil the project objectives? |  | Objective: Activities: |
| 4. | Do you know about any other actives even if you or your organization were not directly involved? | Y/N | Describe: |
| 5. | Do you think these activities were relevant and effective for fulfilling the objectives? | A little/Somewhat/Highly | Why? |
| 6. | Was there any particular activity that you believe was most effective? | Y/N | Describe: |
| 7. | Were there any activities that you feel were ineffective and irrelevant? | Y/N | Describe: |
| 8. | Can you suggest other activities that might have been more relevant and/or effective? | Y/N | Describe: |
| 9. | Who or which groups do you believe this project was targeted towards? | Can you think of any body else? | Name groups: |
| 10. | To what extent do you believe this target group was reached and brought into the project activities? | A little/Somewhat/Strongly | Describe: |
| 11. | Do you agree this project will have lasting effects or benefits? | A little/Somewhat/Strongly Why? How? | Give examples: |
| 12. | Has this project changed anything in the way you or your organization behaves or functions? | Y/N Are you doing anything differently as result of project? | Describe: |

Respondent Number _____ Respondent Position Code _____ Interviewer: _________________

| Part A Managerial - Interview Questions for senior members of implementing agencies involved with either Social and/or Clinical services |  |  |  |
| --- | --- | --- | --- |
| Row | Question | Confirmation | Responses |
| 13. | This project was carried on for 2 and half years. How effective were project activates in the early stages compared to the middle and later stages? | What was your experience? | Describe: |
| 14. | Was there any point at which the project seemed to “take-off” and make good progress | Y/N Why did this happen? | Describe: |
| 15. | Can you identify one or two main areas where some change might have made this project more effective | Y/N | Describe: |
| 16. | In this project did you or your organization have to coordinate or cooperate with people from outside organizations? | Y/N What organisation and In what way? | Describe: |
| 17. | What was your experience in dealing with outside organizations? | Positive/ Neither positive or negative/ Negative | Describe your experience:: |
| 18. | Concerning coordination with outside organizations and people can you think of anything that could or should have been done differently? | Y/N Why? How? | Describe: |
| 19. | Do you have any concerns about any aspect of this project including its purpose design, activities, management etc | Y/N | Describe: |
| 20. | Can you suggest any good lessons that could be learned from this project | Y/N | Describe: |
| 21. | If this lesson was taken seriously how might it change your organization and/or your own activities |  | Describe: |
| 22. | In the locality where you work, to what extent do you feel that people are aware of this project or programme? | A little/Somewhat/Highly Were there any newspaper, radio, TV reports or community meetings? | Describe: |
| 23. | Do you agree that this project focused on migrant worker communities (i.e. sending people to work in India) | Y/N Why? |  |
| 24. | In your experience with this project did you have any direct contact with migrant workers? | Y/N | Describe: |

Respondent Number _____ Respondent Position Code _____ Interviewer: _________________

| Part A Managerial - Interview Questions for senior members of implementing agencies involved with either Social and/or Clinical services |  |  |  |
| --- | --- | --- | --- |
| Row | Question | Confirmation | Responses |
| 25. | If yes can you know the communities they come from | Caste, District, Village locality etc | Describe: |
| 26. | Do you believe any particular communities were dominant | Caste, District, Village locality etc | Describe: |
| 27. | Do you have any idea of the gender make up of migrant workers you have come into contact with? | Y/N Single males Family groups Single females |  |
| 28. | Are you aware of women migrant workers? | Y/N What was their work purpose? | Describe: |
| 29. | Do you believe this project reached people of these communities effectively | Y/N Why? | Describe: |
| 30. | Were there any communities or groups that you feel the project did not reach or did not reach effectively? | Y/N | Describe: |
| 31. | What do you think has been the impact or effect of this project on the targeted groups and on the wider community? | A little/Some/High What kind of impact? | Describe: |
| 32. | To what extent do you think that people in your area are aware of HIV and how it can be passed from person to person? | A little/Some/High Why? | Describe: |
| 33. | Do you think that the project activities have resulted in any identifiable changes in people’s risk behaviour | High/Some/Little Why? | Describe: |
| 34. | This project required certain resources. In your organization and in your own work were relevant resources expert help, training and information made available? What kind of resources were they? | Expert help Training Information Materials | Describe: |
| 35. | Were the relevant resources provided? | Y/N | Describe: |
| 36. | What was the availability and quality of these resources? | Too little/Just right/Too much Quality good or inadequate? | Describe: |
| 37. | Did these resources arrive at the right time? | Y/N | Describe: |

Respondent Number _____ Respondent Position Code _____ Interviewer: _________________

| Part A Managerial - Interview Questions for senior members of implementing agencies involved with either Social and/or Clinical services |  |  |  |
| --- | --- | --- | --- |
| Row | Question | Confirmation | Responses |
| 38. | Could you or your organization have been more effective if you had different and or more resources? | Y/N How? | Describe: |
| 39. | Do you believe your organization has achieved greater capability as result of training given and experience gained | A little/Somewhat/Highly | Describe: |
| 40. | All projects require some kinds of measurements, analysis, and reporting. Were you involved in this area? | Y/N | Describe: |
| 41. | Do you believe that the project information collection and reporting in your organization or your area was complete, accurate, and on time? | Y/N Complete Accurate On time | Describe: |
| 42. | Do you feel that information collection, analysis and reporting could have been improved? | Y/N How? | Describe: |
| 43. | In your organization or your personal experience concerning this project, were there any remarkable success stories or positive experiences that you would like to tell us about? | Y/N What is the key point? | Describe: |
| 44. | In your organization or your personal experience concerning this project, were there any remarkable failures disasters or difficult experiences that you would like to tell us about? | Y/N What is the key point? | Describe: |
| 45. | Did you or your organization come into contact with any foreign representatives or volunteers connected with this project? | Y/N How did they contribute to the success or failure of the project? | Describe: |
| 46. | Did you have direct contact with migrant workers targeted through this project? | Y/N Who? What kind of contact? | Describe: |
| 47. | If you had direct contact in either social service or medical capacity did this project bring up or raise any ethical or moral issues? | - Confidentiality - Human rights - Professional practice - Religious/moral concerns - Conflict of interest - Other | Describe your experience: |

Respondent Number _____ Respondent Position Code _____ Interviewer: _________________

| Part A Managerial - Interview Questions for senior members of implementing agencies involved with either Social and/or Clinical services |  |  |  |
| --- | --- | --- | --- |
| Row | Question | Confirmation | Responses |
| 48. | What do you believe was or is the underlying motivation for this project? | - Establish approaches and methods to make migration safer - Identify and treat maximum number of HIV/AIDS/STI cases - Increase numbers using ART - Minimize transmission of HIV - Other | Describe: |
| 49. | Can effectiveness in reducing HIV transmission be measured? | Y/N How? | Describe: |
| 50. | Should there be official control over migrant workers involving pre and post migration health testing? | Y/N Why? | Describe: |
| 51. | Do you know why your organization was selected to participate in this project? | Y/N Why? | Describe: |
| 52. | If your organization wanted to continue with the activities from this project would you need any additional resources? | Y/N Staff Materials Skills Training | Describe: |
| 53. | If another similar programme was started would you or your organization want to participate? | Y/N Why? | Describe: |
| 54. | Thank you is there anything else you would like to tell me or any question you want to ask me? | Y/N What? | Describe: |

6.1.2 RAB Project Evaluation

Respondent Questionnaire

Respondent Number _____ Respondent Position Code _____ Interviewer: _________________

| Part B Technical - Interview Questions for Clinicians and Laboratory Staff |  |  |  |
| --- | --- | --- | --- |
| Row | Question | Confirmation | Responses |
| 1. | For this project did you receive any particular (subject related) training and orientation? | Y/N What? | Describe: |
| 2. | Were you given training on the correct way to conduct patient interviews, counselling and for giving instructions? | Y/N What? | Describe: |
| 3. | Was any medical equipment, or machines provided for this project? | Y/N What? | Describe: |
| 4. | Was the equipment functioning properly when delivered and is it still working well? | Y/N Why | Describe: |
| 5. | Were you provided with X-ray equipment? | Y/N What? | Describe: |
| 6. | Can you show me the medical equipment that was supplied? | Y/N What is the condition now? | Describe |
| 7. | Were you provided with any kind of medical supplies? | Y/N What were they? | Describe: |
| 8. | Were these supplies sufficient? | Y/N Did you ever run out of stock? | Describe: |
| 9. | Were the supplies of good quality? | Y/N Why? | Describe: |
| 10. | What was the effect of this project on your workload | High/Medium/Low | Describe: |
| 11. | Did you need extra help to interview or examine the patients? | Y/N Why? | Describe: |
| 12. | Do you conduct STI & HIV testing? | Y/N Where? Frequency? Who refers? What procedure do you follow? Male/Female proportions? | Describe: |

Respondent Number _____ Respondent Position Code _____ Interviewer: _________________

| Part B Technical – Interview Questions for Clinicians and Laboratory Staff |  |  |  |
| --- | --- | --- | --- |
| Row | Question | Confirmation | Responses |
| 13. | Do patients always continue with their treatment plan? | Y/N How many drop out? Why? Who follows-up? | Describe: |
| 14. | Have you lost any patients as a result of death? | Y/N How many? When? Why? | Describe? |
| 15. | Do you conduct any home based treatment? | Y/N How many? Where? | Describe: |
| 16. | Does Home Based treatment work well? | Y/N Why? How could it be improved? | Describe: |
| 17. | Do you have any procedures for pregnant women who are HIV+ | Y/N What are they? | Describe: |
| 18. | Thank you is there anything else you would like to tell me or any question you want to ask me? | Y/N What? | Describe: |

6.1.3 RAB Project Evaluation

Respondent Questionnaire

Respondent Number _____ Respondent Position Code _____ Interviewer: _________________

| Part C Patient at Clinic – Interview Questions for Patients |  |  |  |
| --- | --- | --- | --- |
| Row | Question | Confirmation | Responses |
| 1. | Can you tell me about the treatment you are receiving? | Y/N? Why is it needed? When and where did you start to become unwell? Who referred you for treatment? How long have you been receiving treatment? What kind of treatment do you get? How long do expect it to continue? | Describe: |
| 2. | What information were you given about your health, treatment and prevention of passing illness to others? | None/Some/Much What were you told? | Describe: |
| 3. | What does your family and neighbours know about your health condition? | Nothing/Some/Everything | Describe: |
| 4. | Have you been given any advice about healthy living, hygiene diet, and keeping well? | Y/N What advice? Who gave advice? | Describe: |
| 5. | Was this advice helpful? | Y/N What have you been able to use? | Describe: |
| 6. | Can you tell me about your medicines? | Y/N Can you show me? Do you know what they are? Any needles? How often do you take them? Any particular time? Do you need help for treatment Who helps you? | Describe: |
| 7. | How do you feel about your treatment? | Good/OK/Bad Why? | Describe: |

Respondent Number _____ Respondent Position Code _____ Interviewer: _________________

| Part C Patient at Clinic – Interview Questions for Patients |  |  |  |
| --- | --- | --- | --- |
| Row | Question | Confirmation | Responses |
| 8. | Do you ever feel ill or get any effects from the medicines? | Y/N What? | Describe: |
| 9. | How do you feel about coming here and how well do staff members treat you? | Good/OK/Bad Any complaints or suggestions? | Describe: |
| 10. | Do you ever have to stay here overnight for your treatment? | Y/N What accommodation do you use? Is it Good/OK/Bad? | Describe: |
| 11. | How do you feel about yourself and how are you treated by your family, neighbours, and community? | Good/OK/Bad | Describe: |
| 12. | Have you ever had to pay money for anything related to your treatment? | Y/N What for? How much? | Describe: |
| 13. | Are you in contact with any community based organizations? | Y/N Who are they? Where are they from? How do they help you? | Describe: |
| 14. | Do you have sufficient income? | Y/N What is your source of livelihood? | Describe |
| 15. | What is the health status of your family members (Spouse/Children)? | Good/Not good Do you have any Children? | Describe |
| 16. | Are any other family members receiving treatment? | Y/N Who? What kind of treatment Why do they need this treatment? | Describe: |
| 17. | Have you or any of your family members been outside Nepal? | Y/N Who went? When did they go? Where did they go? Why did they go? | Describe: |

Respondent Number _____ Respondent Position Code _____ Interviewer: _________________

| Part C Patient at Clinic – Interview Questions for Patients |  |  |  |
| --- | --- | --- | --- |
| Row | Question | Confirmation | Responses |
| 18. | What is your community affiliation? | District Locality/Village Caste | Describe: |
| 19. | If female: Are you pregnant: | Y/N If yes When was your last menstrual period? Are you receiving any special services? Can you tell me about them? | Describe: |
| 20. | Thank you is there anything else you would like to tell me or any question you want to ask me? | Y/N What? | Describe: |

6.1.4 RAB Project Evaluation

Respondent Questionnaire

Respondent Number _____ Respondent Position Code _____ Interviewer: _________________

| Part D Patient at Home – Interview Questions for Patients |  |  |  |
| --- | --- | --- | --- |
| Row | Question | Confirmation | Responses |
| 1. | Can you tell me about the treatment you are receiving? | Y/N? Why is it needed? When and where did you start to become unwell? Who referred you for treatment? How long have you been receiving treatment? What kind of treatment do you get? How long do expect it to continue? | Describe: |
| 2. | What information were you given about your health, treatment and prevention of passing illness to others? | None/Some/Much What were you told? | Describe: |
| 3. | What does your family and neighbours know about your health condition? | Nothing/Some/Everything | Describe: |
| 4. | Have you been given any advice about healthy living, hygiene diet, and keeping well? | Y/N What advice? Who gave advice? | Describe |
| 5. | Was this advice helpful? | Y/N What have you been able to use? | Describe: |
| 6. | Can you tell me about your medicines? | Y/N Can you show me? Do you know what they are? Any needles? How often do you take them? Any particular time? Do you need help for treatment Who helps you? | Describe: |
| 7. | How do you feel about your treatment? | Good/OK/Bad Why? | Describe: |

Respondent Number _____ Respondent Position Code _____ Interviewer: _________________

| Part D Patient at Home – Interview Questions for Patients |  |  |  |
| --- | --- | --- | --- |
| Row | Question | Confirmation | Responses |
| 8. | Do you ever feel ill or get any effects from the medicines? | Y/N What? | Describe: |
| 9. | How do you feel about yourself and how are you treated by your family, neighbours, and community? | Good/OK/Bad | Describe: |
| 10. | Does anyone come to see you and check your treatment? | Y/N Who comes? How often? What do they do? How do you feel about these visits? | Describe: |
| 11. | Have you ever had to pay money for anything connected with your treatment? | Y/N What for? How much? | Describe: |
| 12. | Are you in contact with any community based organizations? | Y/N Who are they? Where are they from? How do they help you? | Describe: |
| 13. | Do you have sufficient income? | Y/N What is your source of livelihood? | Describe |
| 14. | What is the health of your family members? | Good/Not good Do you have any Children? | Describe |
| 15. | Are any other family members receiving treatment? | Y/N Who? What kind of treatment Why do they need this treatment? | Describe: |
| 16. | Have you or any of your family members been outside Nepal? | Y/N Who went? When did they go? Where did they go? Why did they go? | Describe: |

Respondent Number _____ Respondent Position Code _____ Interviewer: _________________

| Part D Patient at Home – Interview Questions for Patients |  |  |  |
| --- | --- | --- | --- |
| Row | Question | Confirmation | Responses |
| 17. | What is your community affiliation? | District Locality/Village Caste | Describe: |
| 18. | If female: Are you pregnant: | Y/N If yes When was your last menstrual period? Are you receiving any special services? Can you tell me about them? | Describe: |
| 19. | Thank you is there anything else you would like to tell me or any question you want to ask me? | Y/N What? | Describe: |

6.1.5 RAB Project Evaluation

Respondent Questionnaire

Respondent Number _____ Respondent Position Code _____ Interviewer: _________________

| Part E Financial – Interview & Questions for senior managers responsible for Accounting and/or Financial Controls in implementing agencies |  |  |  |
| --- | --- | --- | --- |
| Row | Question | Confirmation | Responses |
| 1. | Can you tell me about the financial objectives (budgets) and controls (measurements and reports) that were established for this project within your organisation or for your department or work area? | Y/N If no, who can? If yes, what are they? Who is responsible for managing them? | Describe: |
| 2. | How were the relevant budgets established? | - Negotiated directly between your organisation and the funding agency - Decided by the funding agency without negotiation - Some other method | Describe: |
| 3. | Considering the workload and expenses involved, do you believe he budgets were: | - Inadequate - Adequate - Generous | Describe: |
| 4. | Did your organisation receive any direct payments for this project | Y/N How much? | Describe: |
| 5. | How were funds channelled to your organisation or department? | - Separate bank account - Organisation’s bank account | Describe: |
| 6. | Can you tell me how you kept a record of expenses and other expenditure for this project | Y/N Can you show me the system? Are you satisfied with the accounting? | Describe: |
| 7. | Do you have a system of accrual for expenses committed but no yet booked? | Y/N How is this area managed? | Describe: |
| 8. | Can you tell me how do you control actual expenses against budgets? | Y/N Can you show me the system? How is this information used? Are you satisfied with the control system? | Describe: |

Respondent Number _____ Respondent Position Code _____ Interviewer: _________________

| Part E Financial – Interview & Questions for senior managers of implementing agencies responsible for Accounting and/or Financial Controls |  |  |  |
| --- | --- | --- | --- |
| Row | Question | Confirmation | Responses |
| 9. | Can you tell me how you determine overheads for this project? | Y/N Actual? Apportionment? Some other method? | Describe: |
| 10. | Did you receive any financial training or assistance to manage this project? | Y/N What kind? | Describe |
| 11. | Have your accounts been audited? | Y/N When? By Whom? | Describe: |
| 12. | Comparison of the Budget vs. Actual expenditure as at July 2008 and the revised budget of the same date shows a substantial deviation resulting from growth in both administrative costs i.e. (salaries, consultants fees and other direct costs) and also overhead costs, at a point where the project had only a further 9 months to run. Can you explain the reason for these deviations from budget? | - Was this substantial increase in expenses due to a significant change in project function? - What will be the actual administrative cost of the project when the administrative costs incurred by the implementing partners are separated out? | Describe: |
| 13. | Can you provide a year to year Budget vs. Actual expenditure statement covering the entire project period? | Y/N Please include all major expense heads | Please provide: |
| 14. | Can you provide a description of the accounting system followed, funds receipt modality (one time grant or reimbursement basis) and was a separate ledger system set up specifically for this project? | Y/N Please provide detailed answers | Please provide: |
| 15. | Do you have any financial rules, policy & procedures document including financial delegation authority | Y/N Please provide detailed answers | Please provide: |
| 16. | Do you have an internal audit system? | Y/N If yes please provide copy of report including preliminary report of external auditors. If no how is the checks and control mechanism operated? | Please provide: Describe: |

Respondent Number _____ Respondent Position Code _____ Interviewer: _________________

| Part E Financial – Interview & Questions for senior managers of implementing agencies responsible for Accounting and/or Financial Controls |  |  |  |
| --- | --- | --- | --- |
| Row | Question | Confirmation | Responses |
| 17. | Is your organisation registered with the Tax Office? | Y/N Do you have a tax exemption certificate? Are annual returns filed with the Tax Office? | Describe: |
| 18. | Do you have a purchasing and procurement approval process | Y/N What authorities are required? | Describe: |
| 19. | Can you provide details of income tax on staff salaries deposited with the Tax Office? | Y/N If no Why? Please provide details for the entire project period | Please provide: |
| 20. | Do you pay any other forms of tax including tax on rents and TDS on payments? | Y/N If no Why? Please provide details for the entire project period | Please provide: |
| 21. | Do you have a fixed assets register? | Y/N If no Why? What is the asset inventory verification period? Please provide details of fixed assets related to this project at time of project completion. | Please provide: |
| 22. | Were any fixed assets purchased under the Customs Duty favour system? | Y/N Please detail | Please provide |
| 23. | Do you have a stock keeping record for consumable items related to this project? | Y/N If no Why? What is the stock inventory verification period? Please provide details of stock on hand at the time of project completion and their intended future use. | Please provide: |
| 24. | Do you have a process is for controlling the financial transactions with local partner agencies? | Y/N What is it? | Please describe |

6.1.6 RAB Project Evaluation

Respondent Questionnaire

Respondent Number _____ Respondent Position Code _____ Interviewer: _________________

| Part F Project Owner - Interview Questions for senior managers responsible for designing and promoting this Project |  |  |  |
| --- | --- | --- | --- |
| Row | Question | Confirmation | Responses |
| 1. | The RAB project has demonstrated that out of some 8,000 VCT subjects, nearly 600 tested HIV+. Do you believe that this is a representative sample and may be a fair indication of the real infection rate among male Nepalese workers on short to medium term migration to and from India? | Y/N If not, Why? Do you therefore agree that HIV infection among male migrants may be in the region of 7.5% | Comment: |
| 2. | In your project background narrative, you mention that STI/HIV behavioural data indicates that male migrants to India number in the range of 6,00,000 to 12,00,000. You also suggest that the annual migration to India may be responsible for 30-50% of the current HIV burden in Nepal. What is the source of this information and can we be more precise about migrant numbers? Also how do you arrive at the 30-50% estimate? | Y/N Why? | Comment: |
| 3. | If the infection rate among male migrants is in region of 7.5% your figures for total migration suggest that between 50,000 and 1,00,000 HIV carriers may be entering Nepal from India every year. Do you agree? | Y/N Why? | Comment: |
| 4. | Have you incorporated any particular factors or methods into the project design that allow you to demonstrate or claim to measure effectiveness in reducing HIV transmission? | Y/N What were they? | Comment: |
| 5. | There is an old adage that ‘Prevention is better than Cure’. What was the approximate proportion of the total RAB project resources that were committed to prevention versus treatment? What was the reason for this relative allocation and could or should there have been a greater emphasis on prevention? | Y/N Why? | Comment: |

Respondent Number _____ Respondent Position Code _____ Interviewer: _________________

| Part F Project Owner - Interview Questions for senior managers responsible for designing and promoting this Project |  |  |  |
| --- | --- | --- | --- |
| Row | Question | Confirmation | Responses |
| 6. | Have you considered the globally accepted standard approach of using only SMART Objectives? Specific Measureable Achievable Relevant Time-bound | Y/N If not why? | Comment: |

6.2 Photographs

SECTION VII - APPENDICES

7.1 Project Logical Framework